## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Gosaba (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001888/2022-2023 | 10940/AD | 06/02/2023 | 23/03/2023 | M/S R.DUTTA & CO. | 6.94 | 6.94 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 112/AD | 13/04/2023 | 13/04/2023 | Resource Division | 0.34 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000132/2023-2024 | 843/AD | 27/05/2023 | 27/05/2023 | Resource Division | 1.72 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Construction of boundary wall at Head Work Site for Ground Water Based at Gosaba (Zone-I) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001230/2024-2025 | 5211/AD | 16/12/2024 | 30/01/2025 | SARADA CONSTRUCTION | 32.99 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000406/2023-2024 | 360/AD | 19/01/2024 | 19/01/2024 | Resource Division | 15.52 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000720/2023-2024 | 542/AD | 25/01/2024 | 25/01/2024 | Resource Division | 161.43 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Construction of OHR (250 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the Gosaba (Zone-I), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000484/2023-2024 | 1997/AD | 04/08/2023 | 28/08/2024 | DIVINE | 617.63 | 384.47 | 62.25 | 65
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Laying of additional pipe line at Augmentation of Gosaba W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000309/2024-2025 | 2690/AD | 24/06/2024 | 17/10/2025 | B.S. CONSTRUCTION | 56.54 | 0 | 0 | 30
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Renovation and retrofitting of Pump House No. 3 of Augmentation of Gosaba W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000183/2025-2026 | 546/CSD | 30/04/2025 | 30/05/2025 | M/S JBL CONSTRUCTION | 2.27 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Renovation and retrofitting of Pump House No. 3 of Augmentation of Pathankhali W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000299/2025-2026 | 545/CSD | 30/04/2025 | 30/05/2025 | A.K. ENTERPRISE | 2.22 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Renovation and retrofitting of Pump House No. 2 of Augmentation of Gosaba W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000300/2025-2026 | 556/CSD | 02/05/2025 | 01/06/2025 | NILKANTHA ENTERPRISE | 2.29 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/15056 | Augmentation | Renovation and retrofitting of Pump House No. 1 of Augmentation of Gosaba W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000728/2025-2026 | 642/CSD | 23/05/2025 | 22/06/2025 | ASIK CONSTRUCTION | 2.29 | 0 | 0 | 0
Total | [13 empty] | 902.19 | 391.4 | 43.38