## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Canning-II, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division |  | ORD/000085/2020-2021 | 5308/AD | 18/02/2021 | 18/02/2022 | NATURAL RESOURCES CONSORTIUM | 89.65 | 0 | 0 | 77
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Laying of DI pipe to connect OHR with rising main and distribution system at Srinagar W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000994/2021-2022 | 989/CSD | 26/10/2021 | 25/11/2021 | K.P. CONSTRUCTION | 4.21 | 0 | 0 | 90
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Earth working embankment at Head work site of Srinagar Water Supply Scheme, Block-canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000003/2022-2023 | 120/AD | 07/04/2022 | 14/04/2022 | SWASTIK CONSTRUCTION | 8.31 | 0 | 0 | 97
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households at Srinagar Water Supply Scheme (Habitation- Mollapara, Sekhpara & Majherpara), Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/000112/2022-2023 | 295/CSD | 20/05/2022 | 29/06/2022 | RAJLAKSHMI ENTERPRISE | 4.81 | 0 | 0 | 77
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 221/AD | 21/04/2023 | 21/04/2023 | Resource Division | 64.05 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Srinagar W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001690/2022-2023 | 11261/AD | 18/02/2023 | 21/09/2024 | RAHUL ENTERPRISE | 7.05 | 0 | 0 | 99
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Construction of 1 (one) no. Store Room (multipurpose) (4.88m x 3.66m) at head work site of Srinagar Water Supply Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000062/2022-2023 | 843/AD | 13/05/2022 | 12/06/2022 | BHUNIA BUILDERS | 5.95 | 0 | 0 | 80
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households at Srinagar Water Supply Scheme (Habitation- Banamalipur Khanpara), Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/000089/2022-2023 | 293/CSD | 20/05/2022 | 29/06/2022 | NATURAL RESOURCES CONSORTIUM | 4.83 | 0 | 0 | 87
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Augmentation of Srinagar W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001671/2022-2023 | 11482/AD | 15/02/2023 | 17/03/2023 | TRIMURTI ENTERPRISE | 19.58 | 0 | 0 | 98
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Srinagar Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001999/2022-2023 | 12813/AD | 16/03/2023 | 15/05/2023 | SAHANA ENTERPRISE | 52.81 | 0 | 0 | 99
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Inter connection and rising main with supply of specials at PH-IV of Srinagar W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002000/2022-2023 | 12814/AD | 16/03/2023 | 01/01/2026 | NATURAL RESOURCES CONSORTIUM | 65.73 | 0 | 0 | 55
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Srinagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000039/2023-2024 | 994/SMD | 06/04/2023 | 30/12/2025 | A.G.ENTERPRISE | 11.15 | 0 | 0 | 95
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House-1 of Aug of Srinagar water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15095) | Assistant Engineer | Junior Engineer | ORD/002198/2024-2025 | 1522/SMSD | 18/11/2024 | 03/12/2024 | A.G.ENTERPRISE | 0.92 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15095 | Augmentation | Supply & fixing main switch & Bus Bar at Pump House-1 of Aug of Srinagar water supply scheme under SMD,PHE Dte. (Block-Canning-II) (SM/15095) | Assistant Engineer | Junior Engineer | ORD/002199/2024-2025 | 1523/SMSD | 18/11/2024 | 03/12/2024 | A.G.ENTERPRISE | 0.29 | 0 | 0 | 0
Total | [13 empty] | 339.36 | 0 | 0