## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 269/AD | 24/04/2023 | 24/04/2023 | Resource Division | 64.87 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Payment of Electric Bill for new service connection under SMD PHE Dte. |  |  | BILL/00282/2023-2024 | BP-2023-24-15 | 15/05/2023 | 15/05/2023 | WBSEDCL | 3.53 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00748/2023-2024 | BP-2023-24-102 | 04/07/2023 | 04/07/2023 | WBSEDCL | 3.51 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Sinking of 02 (two) Nos. of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using UPVC pipe (CD) and UPVC Deep well screen (RDS) pipe with ribs pipe at Tube Well No. - 3 of Augmentation of Kalaria (Zone-IIA) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001673/2022-2023 | 11484/AD | 15/02/2023 | 01/04/2023 | B.K. ENTERPRISE. | 40.73 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Kalaria (Zone-IIA) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001949/2022-2023 | 10893/AD | 04/02/2023 | 21/03/2023 | SIRCON ENGINEERING SERVICES | 6.76 | 0 | 0 | 90
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIA), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000255/2023-2024 | 1398/AD | 12/07/2023 | 26/08/2023 | M/S. MA BHABANI CONSTRUCTION | 7.25 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Quotation for new service( power) connection at Kalaria Zone-IIA PH-2 Water supply scheme under Canning-I block. Reference ID:-106599054, Application No :-1007770612 |  |  | BILL/00376/2024-2025 | BP-2024-25-96 | 10/06/2024 | 10/06/2024 | WBSEDCL | 5.51 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Quotation for new service ( power) connection at kalaria Zone-II A, PH-1 Water supply scheme under canning-I block Reference ID-106621217 Application No-1007825764 |  |  | BILL/01482/2024-2025 | BP-2024-25-349 | 06/09/2024 | 06/09/2024 | WBSEDCL | 11.75 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Kalaria ( Zone-II A) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000024/2023-2024 | 958/SMD | 04/04/2023 | 02/04/2025 | ASHUTOSH DAS & CO. | 38.89 | 0 | 0 | 60
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017473) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000357/2023-2024 | 1687/AD | 21/07/2023 | 11/01/2025 | NEW STAR CONSTRUCTION | 137.02 | 0 | 0 | 96
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2430] (TSM/017473) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000356/2023-2024 | 1686/AD | 21/07/2023 | 08/10/2025 | NEW STAR CONSTRUCTION | 132.25 | 0 | 0 | 25
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIA) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000025/2025-2026 | 2011/AD | 28/04/2025 | 28/05/2025 | HALDER & CO. | 8.53 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Construction of boundary wall at Pump House No. - 4 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIA) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000026/2025-2026 | 2012/AD | 28/04/2025 | 28/05/2025 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 7.84 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/15100 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIA), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001510/2023-2024 | 4748/AD | 19/12/2023 | 27/01/2025 | MALANCHA CONSTRUCTION | 7.06 | 0 | 0 | 100
Total | [13 empty] | 475.5 | 0 | 0