## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chunakhali W/S Scheme (Zone-II), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001710/2022-2023 | 11674/AD | 20/02/2023 | 06/04/2023 | A.K. ENTERPRISE | 7.07 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chunakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001709/2022-2023 | 11673/AD | 20/02/2023 | 06/04/2023 | A.K. ENTERPRISE | 7.07 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Chunakhali Zone1 & 2 water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/000015/2023-2024 | 950/SMD | 04/04/2023 | 03/07/2023 | BARISAL TRADING CO. | 21.4 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Construction of 1 (one) no. Switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Chunakhali W/S Scheme, Block : Basanti under Canning Sub-Division of Alipore Division, PHE Dte.[Pump House-3] |  |  | ORD/003185/2020-2021 | 322/AD | 08/06/2020 | 08/06/2020 | M/S. MIHIR KUMAR NASKAR | 5.08 | 4.95 | 97.46 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Surging of 03 (three) nos. 250mm x 150mm. dia. 360 mtr. Deep Tubewell at Chunakhali W/S Scheme (Zone-II) TW-1, 2 & 3 under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001746/2020-2021 | 1448/CSD | 27/01/2021 | 11/02/2021 | AQUATECH ENGINEER | 2.01 | 2.01 | 100 | 54
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Protection of pipe line and inter connection in-between existing rising main and TW No. - 3 at Chunakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000995/2021-2022 | 990/CSD | 26/10/2021 | 25/11/2021 | MODERN CONSTRUCTION | 3.14 | 3.04 | 96.76 | 54
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using UPVC pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Chunakhali Water Supply Scheme (Zone-II) Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001575/2021-2022 | 6956/AD | 30/03/2022 | 29/04/2022 | AQUATECH ENGINEER | 17.84 | 4.45 | 24.95 | 54
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000113/2022-2023 | 245/AD | 24/04/2023 | 24/04/2023 | Resource Division | 159.84 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone - I & II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000336/2023-2024 | 1553/AD | 17/07/2023 | 15/10/2023 | TIYASHA ENTERPRISE | 140.12 | 110.35 | 78.76 | 80
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Surging of 1no. Big dia Tubewell of Chunakhali (Zone - I & II) W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.E. Dte. (Zon-II, TW-3) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001682/2023-2024 | 1359/CSD | 19/12/2023 | 02/02/2024 | S.K.GOLUI | 3.89 | 3.77 | 96.83 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000398/2023-2024 | 356/AD | 19/01/2024 | 19/01/2024 | Resource Division | 9.24 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Restoration of Kanthalberia Chunakhali Road block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division |  |  | BILL/01325/2024-2025 | BP-2024-25-625 | 27/09/2024 | 27/09/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 60.02 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15104 | Augmentation | Interconnection & rising main with supply of specials for each zone of Chunakhali (Zone - I & II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000339/2023-2024 | 3739/AD | 03/11/2023 | 25/07/2026 | BUILDERS | 67.39 | 0 | 0 | 40
Total | [13 empty] | 504.11 | 128.57 | 25.5