## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15107 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 5 of Augmentation of Budhkhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001666/2022-2023 | 11478/AD | 15/02/2023 | 17/03/2023 | M.R.ENTERPRISE (II) | 19.52 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15107 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001704/2022-2023 | 11668/AD | 20/02/2023 | 06/04/2023 | BABAMONI CONSTRUCTION | 7.09 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15107 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Budhkhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000025/2023-2024 | 959/SMD | 04/04/2023 | 03/07/2023 | JYOTY SOLAR POWER | 11.16 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15107 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000337/2023-2024 | 1939/AD | 02/08/2023 | 31/10/2023 | KIRON CONSTRUCTION | 126.68 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15107 | Augmentation | Inter connection and rising main with supply of specials at PH-V of Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division |  | ORD/000735/2023-2024 | 2896/AD | 19/09/2023 | 04/10/2023 | SUPER CONSTRUCTION | 37.51 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15107 | Augmentation | Surging of 1no. Big dia Tubewell of Budhkhali W/S Scheme under JJM, Block - Canning - I under Canning Sub-Division under Alipore Division P.H.E. Dte. (TW-2) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001680/2023-2024 | 1357/CSD | 19/12/2023 | 18/01/2024 | S.K.GOLUI | 2.85 | 2.16 | 75.75 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15107 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 272/AD | 24/04/2023 | 24/04/2023 | Resource Division | 88.67 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15107 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Budhkhali W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - VI) (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000782/2024-2025 | 4483/AD | 11/11/2024 | 11/12/2024 | B.K. ENTERPRISE. | 19.35 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15107 | Augmentation | Inter connection & rising main with supply of specials at Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002551/2024-2025 | 1414/CSD | 10/12/2024 | 04/01/2025 | ASHIS ENTERPRISE | 0.49 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15107 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Budhkhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (TW No. 2 alternative Tubewell) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002377/2023-2024 | 1201/AD | 29/02/2024 | 30/03/2024 | BHATTACHARJEE & CO. | 19.52 | 16.96 | 86.87 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15107 | Augmentation | Quotation for new service ( power ) connection at Budhakhali PH-5 under Canning -I block (REF ID : 106673108) (APP ID: 1007939044) |  |  | BILL/01157/2024-2025 | BP-2024-25-233 | 08/08/2024 | 08/08/2024 | WBSEDCL | 4.32 | 0 | 0 | 0
Total | [13 empty] | 337.14 | 19.12 | 5.67