## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Mallik Kati W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001684/2022-2023 | 11491/AD | 15/02/2023 | 01/04/2023 | M/S M.B.ENTERPRISE | 7.07 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 113/AD | 13/04/2023 | 13/04/2023 | Resource Division | 0.34 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 855/AD | 27/05/2023 | 27/05/2023 | Resource Division | 1.72 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 223/AD | 21/04/2023 | 21/04/2023 | Resource Division | 174.21 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mallik Kati Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000323/2023-2024 | 1549/AD | 17/07/2023 | 15/10/2023 | SAJAL KUMAR DAS | 131.07 | 52.1 | 39.75 | 20
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Inter connection and rising main with supply of specials from Head work site to PH-III and Head work site to PH-IV of Mallik Kati W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002002/2022-2023 | 12816/AD | 16/03/2023 | 15/05/2023 | MA KALI CONSTRUCTION | 67.36 | 8.78 | 13.04 | 50
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Quotation for new service ( power ) connection at Mallikati PH-4 under Canning -II block (REF ID : 106665557) (APP ID: 1007923989) |  |  | BILL/01006/2024-2025 | BP-2024-25-207 | 30/07/2024 | 30/07/2024 | WBSEDCL | 13.31 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Quotation for new service ( power ) connection at Mallikati PH-3 under Canning -II block (REF ID : 106665556) (APP ID: 1007924332) |  |  | BILL/01005/2024-2025 | BP-2024-25-206 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.8 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 & 4 of Augmentation of Mallik Kati W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001665/2022-2023 | 11477/AD | 15/02/2023 | 02/05/2025 | SATYAM CONSTRUCTION | 39.13 | 0 | 0 | 50
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 & 2 for Augmentation of Mallik Kati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000037/2023-2024 | 992/SMD | 06/04/2023 | 03/07/2025 | A.G.ENTERPRISE | 22.21 | 0 | 0 | 45
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House-2 of Aug of Mallikkhati water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15196) | Assistant Engineer | Junior Engineer | ORD/002196/2024-2025 | 1785/SMSD | 31/12/2024 | 15/01/2025 | A.G.ENTERPRISE | 0.92 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Mallik Kati W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH No. - 3) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002049/2022-2023 | 13049/AD | 24/03/2023 | 11/01/2025 | BINAPANI ENTERPRISE | 7.1 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Supply & fixing main switch & Bus Bar at Pump House-1, 2 of Aug of Mallikkhati water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15196) | Assistant Engineer | Junior Engineer | ORD/002197/2024-2025 | 1681/SMSD | 23/12/2024 | 07/01/2025 | A.G.ENTERPRISE | 0.59 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15196 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House-1 of Aug of Mallikkhati water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15196) | Assistant Engineer | Junior Engineer | ORD/002200/2024-2025 | 1673/SMSD | 20/12/2024 | 04/01/2025 | A.G.ENTERPRISE | 0.92 | 0 | 0 | 100
Total | [13 empty] | 469.77 | 60.88 | 12.96