## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Inter connection and rising main with supply of specials from Head work site to PH-IV and Head work site to PH-V of Harbhangi W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002044/2022-2023 | 13044/AD | 24/03/2023 | 08/05/2023 | A.S.A.CONSTRUCTION AND CONSULTANT | 23.84 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Chharanekhali & Uttar Sonakhali), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/000088/2022-2023 | 279/CSD | 19/05/2022 | 28/06/2022 | PROJECT & MAINTENANCE | 4.76 | 0 | 0 | 85
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2022-2023 | 247/AD | 24/04/2023 | 24/04/2023 | Resource Division | 195.03 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 848/AD | 27/05/2023 | 27/05/2023 | Resource Division | 1.72 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00750/2023-2024 | BP-2023-24-101 | 04/07/2023 | 04/07/2023 | WBSEDCL | 2.65 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00621/2023-2024 | BP-2023-24-85 | 14/06/2023 | 14/06/2023 | WBSEDCL | 5.61 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (620 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Harbhangi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002004/2022-2023 | 12818/AD | 16/03/2023 | 30/04/2023 | RAKTIM ENTERPRISE | 45.51 | 0 | 0 | 75
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Construction of Sluice Valve Chamber and protection of pipe line work at Augmentation of Harbhangi W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000361/2024-2025 | 731/CSD | 28/06/2024 | 28/07/2024 | A.M. ENTERPRISE | 1.47 | 0 | 0 | 99
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Harbhangi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/000019/2023-2024 | 954/SMD | 04/04/2023 | 03/07/2023 | KARUNAMOY ENGINEERING | 26.02 | 0 | 0 | 80
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.4 of Harbhangi W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti) | Assistant Engineer | Junior Engineer | ORD/002702/2023-2024 | 1078/SMSD | 17/08/2023 | 01/09/2023 | KARUNAMOY ENGINEERING | 0.91 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.5 of Harbhangi W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti) | Assistant Engineer | Junior Engineer | ORD/002703/2023-2024 | 1079/SMSD | 17/08/2023 | 01/09/2023 | KARUNAMOY ENGINEERING | 0.91 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15198 | Augmentation | Surging of 03 nos. Big dia Tubewell of Harbhangi W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.Engg. Dte. (TW-1, 2 & 5) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002976/2024-2025 | 32./CSD | 09/01/2025 | 08/02/2025 | FORTUNE ENGINEERING | 4.3 | 0 | 0 | 0
Total | [13 empty] | 312.72 | 0 | 0