## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Augmentation for Providing Functional Household Tap Connection (FHTC) from Distribution System under Zone - VIIIB & Zone-X at Kulpi Block under "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - X/B) [No. of FHTC = 9578] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000342/2023-2024 | 1560/AD | 17/07/2023 | 15/10/2023 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 512.43 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VIII(B) of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001021/2022-2023 | 294/DHSD | 15/09/2022 | 15/10/2022 | GEO SOLUTION | 3.59 | 3.32 | 92.59 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000146/2022-2023 | 11/AD | 05/04/2023 | 05/04/2023 | Resource Division | 38.18 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000211/2023-2024 | 2020/AD | 05/08/2023 | 05/08/2023 | Resource Division | 12.51 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 1629/AD | 19/07/2023 | 19/07/2023 | Resource Division | 15.54 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-VIII(B) (Lakshmipur, OHR Size-600 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/002100/2022-2023 | 339/DHSD | 17/11/2022 | 24/11/2022 | ASTER CONSULTANCY | 0.5 | 0.5 | 100 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000623/2023-2024 | 284/AD | 15/01/2024 | 15/01/2024 | Resource Division | 24.64 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000939/2023-2024 | 1281/AD | 02/03/2024 | 02/03/2024 | Resource Division | 1.24 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000856/2023-2024 | 763/AD | 03/02/2024 | 03/02/2024 | Resource Division | 7.76 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Land Development and beautification within the head works site under Zone No-VIIIB of Kulpi Block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002150/2024-2025 | 409/AD | 31/01/2025 | 02/03/2025 | S.MISRA INFRADEV PVT. LTD. | 21.56 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Laying of additional pipeline under the Augmentation Scheme of Zone-VIIIB at Kulpi Block for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/15320] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD,Junior Engineer 4 DHSD | ORD/001048/2024-2025 | 4992/AD | 05/12/2024 | 30/03/2026 | SHYAM DEVELOPER | 113.34 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Construction of boundary wall at porposed OHR site at Mouza - Laxmipur under Zone- VIIIB of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD,Junior Engineer DHSD | ORD/001370/2024-2025 | 5499/AD | 27/12/2024 | 10/02/2025 | S.MISRA INFRADEV PVT. LTD. | 22.15 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Construction of pipe carrying structure with laying of 323.9 mm dia. (OD) M.S. distribution line for crossing of Jamtala Canal at Jamtala mouza (Node point 192 to 196) under the Augmentation scheme of Kulpi Zone-VIIIB within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District - South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD,Junior Engineer 4 DHSD | ORD/001021/2024-2025 | 4932/AD | 03/12/2024 | 17/01/2025 | S.MISRA INFRADEV PVT. LTD. | 31.55 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Construction of pipe carrying structure with laying of 323.9 mm dia. (OD) M.S. Distribution line for crossing of Jamtala Canal at Jamtala mouza (Node point 11 to 13) under the Augmentation scheme of Kulpi Zone-VIIIB within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD,Junior Engineer DHSD | ORD/001019/2024-2025 | 4930/AD | 03/12/2024 | 17/01/2025 | S.MISRA INFRADEV PVT. LTD. | 42.5 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/15320 | Augmentation | Construction of pipe carrying structure with laying of 323.9 mm dia. (OD) M.S. Distribution line for crossing of Jamtala Canal at Jamtala mouza (Node point 197 to 206) under the Augmentation scheme of Kulpi Zone-VIIIB within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District - South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD,Junior Engineer DHSD | ORD/001020/2024-2025 | 4931/AD | 03/12/2024 | 17/01/2025 | SELECTION | 51.26 | 0 | 0 | 100
Total | [13 empty] | 898.74 | 3.82 | 0.42