## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Investigation of soil for the proposed 2(two) nos. R.C.C. Over Head Reservoir i.e. at Zone-X (Kuleswar OHR Size-600) and Zone-XI (Mongrajpur OHR Size-250) within Diamond Harbour-I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/000509/2022-2023 | 5530/AD. | 29/09/2022 | 16/01/2025 | NIRMAN (NEW) | 1.56 | 0 | 0 | 50
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-X (Kuleswar OHR Size-600) within Diamond Harbour-I Block under "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas" under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/002090/2022-2023 | 324/DHSD | 07/11/2022 | 14/11/2022 | ASTER CONSULTANCY | 0.5 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-X of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001053/2022-2023 | 306/DHSD | 23/09/2022 | 23/10/2022 | MEASURE LAND | 2.96 | 2.89 | 97.44 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Construction of boundary wall at proposed OHR site at Mouza - Kuleswar under Zone- X of Diamond Harbour-I Block for Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000506/2023-2024 | 1803/AD | 26/07/2023 | 25/08/2023 | A.S.A.CONSTRUCTION AND CONSULTANT | 27.6 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- X at Kuleswar of Diamond Harbour- I block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-4980]. | Assistant Engineer, Diamond Harbour sub division,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/000674/2023-2024 | 2701/AD | 07/09/2023 | 23/02/2026 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 983.37 | 481.06 | 48.92 | 60
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000127/2022-2023 | 28/AD | 05/04/2023 | 05/04/2023 | Resource Division | 14.72 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000348/2023-2024 | 3212/AD | 04/10/2023 | 04/10/2023 | Resource Division | 0.21 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000236/2023-2024 | 2197/AD | 10/08/2023 | 10/08/2023 | Resource Division | 29.99 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/12/2024 to 28/02/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001563/2024-2025 | 700/DHSD | 29/11/2024 | 27/02/2025 | AVIJIT SIL | 1.2 | 1.15 | 95.63 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (Period from 01/05/2024 to 31/10/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 1 DHSD | ORD/000007/2024-2025 | 49/DHSD | 30/04/2024 | 31/10/2024 | SUMAN HALDER | 2.4 | 2.24 | 93.27 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/05/2024 to 31/10/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000006/2024-2025 | 48/DHSD | 30/04/2024 | 31/10/2024 | GOPAL KUMAR JHA | 2.4 | 1.99 | 82.75 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (Period from 01/11/2024 to 30/04/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001039/2024-2025 | 641/DHSD | 30/10/2024 | 29/04/2025 | SUMAN HALDER | 2.4 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Hiring of an Inspection Vehicle for the use of JJM related works under the office of the Assistant Engineer, Diamond Harbour Sub-Division, under Alipore Division, P.H.E. Dte. (period from 01/10/2024 to 31/03/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001042/2024-2025 | 545/DHSD | 30/09/2024 | 31/03/2025 | M.P. ENTERPRISE (II) | 2.4 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/11/2024 to 30/11/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000915/2024-2025 | 642/DHSD | 30/10/2024 | 29/11/2024 | GOPAL KUMAR JHA | 0.4 | 0.39 | 98.08 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Balance works under the Augmentation scheme of Zone-X at Diamond Harbour- I block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division,Assistant Engineer, Raidighi sub division | Junior Engineer 1 DHSD,Junior Engineer 2 DHSD | ORD/000871/2024-2025 | 4655/AD | 20/11/2024 | 15/03/2026 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 81.66 | 0 | 0 | 73
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000894/2023-2024 | 748/AD | 03/02/2024 | 03/02/2024 | Resource Division | 30.68 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (Period from 01/05/2025 to 31/10/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000209/2025-2026 | 74/DHSD | 29/04/2025 | 30/10/2025 | SUMAN HALDER | 2.4 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | SM/15322 | Augmentation | Laying of distribution pipe line of different dia. M.S. and different dia. UPVC pipe line of damage portion due to road widening for 5 nos. culvert crossing with allied works at sonamukhi bridge near Parulia G.P, at Dostipur-Usthi road, at Hatuganje more to Netra stations road and OHR head work site to Hatuganje more road under Augmentation scheme of Diamond Harbour-I Zone-IV, Zone-X & Zone-III within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Parganas under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2 DHSD | ORD/000098/2025-2026 | 2527/AD | 30/05/2025 | 29/07/2025 | SRIJON ENTERPRISE | 89.87 | 0 | 0 | 100
Total | [13 empty] | 1276.71 | 489.72 | 38.36