## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 244/AD | 24/04/2023 | 24/04/2023 | Resource Division | 84.63 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00751/2023-2024 | BP-2023-24-100 | 04/07/2023 | 04/07/2023 | WBSEDCL | 15.67 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Construction of boundary wall at Pump House No. - 2 at Lot No.-126 (Zone-I) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000311/2024-2025 | 2692/AD | 24/06/2024 | 24/07/2024 | SURYA ENTERPRISE | 8.72 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Construction of Toilet including Sanitary arrangement as per departmental drawing at the site for Augmentation of Lot No. 126 (Zone - I & II) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001070/2024-2025 | 1305/CSD | 22/11/2024 | 21/01/2025 | A.P. CONSTRUCTION | 2.09 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Lot-126 (Zone-I & II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001946/2022-2023 | 10894/AD | 04/02/2023 | 21/03/2023 | GANGA TUBEWELL AND HARDWARE | 2.6 | 0 | 0 | 95
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Inter connection and rising main with supply of specials at Augmentation of Lot No. 126 W/S Scheme (Zone-I and II), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Part - B] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002016/2022-2023 | 12922/AD | 21/03/2023 | 20/05/2023 | S.P. CONSTRUCTION (I) | 97.64 | 0 | 0 | 80
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Lot 126 Zone1 & 2 water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/000016/2023-2024 | 951/SMD | 04/04/2023 | 03/07/2023 | BARISAL TRADING CO. | 22.3 | 0 | 0 | 80
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Inter connection and rising main with supply of specials at Augmentation of Lot No. 126 W/S Scheme (Zone-I and II), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Part - A] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002015/2022-2023 | 12921/AD | 21/03/2023 | 20/04/2023 | JYOTI ENTERPRISES | 14.41 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.3 of Lot 126 (Zone-I) W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti) | Assistant Engineer | Junior Engineer | ORD/002704/2023-2024 | 1189/SMSD | 08/09/2023 | 23/09/2023 | BARISAL TRADING CO. | 0.9 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.3 of Lot 126 (Zone-II) W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti) | Assistant Engineer | Junior Engineer | ORD/002705/2023-2024 | 1190/SMSD | 08/09/2023 | 23/09/2023 | BARISAL TRADING CO. | 0.9 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000397/2023-2024 | 355/AD | 19/01/2024 | 19/01/2024 | Resource Division | 4.31 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Augmentation Piped Water Supply Scheme of Lot 126 (Zone - I & II) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Zone - I) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002382/2024-2025 | 619/AD | 17/02/2025 | 19/03/2025 | SURYA ENTERPRISE | 12.58 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15464 | Augmentation | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Augmentation Piped Water Supply Scheme of Lot 126 (Zone - I & II) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Zone - II) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002383/2024-2025 | 620/AD | 17/02/2025 | 19/03/2025 | SURYA ENTERPRISE | 11.46 | 0 | 0 | 0
Total | [13 empty] | 278.22 | 0 | 0