## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-XI, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE D | SM/15466 | Augmentation | Extension of Pipeline at Gabbati of under Ghoradal Water supply Scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001034/2021-2022 | 538/RSD | 30/11/2021 | 29/01/2022 | UNITED BUILDERS | 4.65 | 4.23 | 90.91 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-XI, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE D | SM/15466 | Augmentation | Laying distribution system of piped water supply at Zone- XI of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000877/2024-2025 | 4661/AD | 20/11/2024 | 04/01/2025 | L.N. ENTERPRISE | 17.1 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-XI, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE D | SM/15466 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000606/2023-2024 | 236/AD | 11/01/2024 | 11/01/2024 | Resource Division | 6.75 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-XI, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE D | SM/15466 | Augmentation | Providing FHTC including distribution system and other allied works at Zone- XI of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000025/2023-2024 | 105/AD | 13/04/2023 | 12/10/2025 | SUJATA CONSTRUCTION | 319.09 | 190.77 | 59.79 | 85
Total | [13 empty] | 347.59 | 195 | 56.1