## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XVII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15467 | Augmentation | Laying distribution system of piped water supply at Zone- XVII of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000883/2024-2025 | 4665/AD | 20/11/2024 | 19/01/2025 | SUPRITI ENTERPRISE | 45.45 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XVII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15467 | Augmentation | Construction of 1 no. Pump House of size 4.80 Mtr. X 3.66 Mtr. (as per Dept. drawing) at Zone - XVII Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000884/2024-2025 | 4666/AD | 20/11/2024 | 04/01/2025 | S.S. CONSTRUCTION (NAMKHANA) | 13.11 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XVII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15467 | Augmentation | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Raghudevpur W/S Scheme (Zone-XVII, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001256/2023-2024 | 4181/AD | 28/11/2023 | 28/12/2023 | MEHAI TECHNOLOGY LIMITED | 19.84 | 19.29 | 97.21 | 99
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XVII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15467 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000601/2023-2024 | 229/AD | 11/01/2024 | 11/01/2024 | Resource Division | 5.78 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XVII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15467 | Augmentation | Providing FHTC including distribution system and other allied works at Zone- XVII of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer 3, Raidghi Sub Division | ORD/000132/2023-2024 | 674/AD | 17/05/2023 | 07/08/2025 | BALAJI UDDYOG | 553.99 | 282.29 | 50.96 | 60
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XVII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15467 | Augmentation | Laying distribution system and other allied works for piped water supply at Zone - XVII of Mathurapur- I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/09396 and SM/15467) | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer 3, Raidghi Sub Division | ORD/000533/2024-2025 | 3639/AD | 09/09/2024 | 21/07/2025 | BALAJI UDDYOG | 37 | 0 | 0 | 10
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XVII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15467 | Augmentation | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 02/08/2025 | M/S B. ENTERPRISE | 43.57 | 0 | 0 | 0
Total | [13 empty] | 718.74 | 301.58 | 41.96