## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORK UNDER ZONE-VIII, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15468 | Augmentation | Construction of approach road at the Head work site of Mirjapur W/S Scheme, modified as Zone- VIII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  | Junior Engineer 2, Raidghi Sub Division | ORD/001179/2023-2024 | 358/RSD | 21/11/2023 | 20/01/2024 | M/S M.B.ENTERPRISE | 3.29 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORK UNDER ZONE-VIII, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15468 | Augmentation | Protection work at the Head work site of Mirjapur W/S Scheme, modified as Zone- VIII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001178/2023-2024 | 357/RSD | 21/11/2023 | 20/01/2024 | M/S. GANGA ENTERPRISE | 2.94 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORK UNDER ZONE-VIII, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000248/2023-2024 | 3105/AD | 28/09/2023 | 28/09/2023 | Resource Division | 13.4 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORK UNDER ZONE-VIII, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15468 | Augmentation | Contruction of 400 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Construction of Boundary wall, Providing FHTC including distribution system and other allied works at Zone- VIII of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer-1, South 24 WS Circle. | ORD/000631/2023-2024 | 3731/AD | 03/11/2023 | 20/06/2026 | MONDAL CONSTRUCTION NEW | 366.12 | 0 | 0 | 5
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORK UNDER ZONE-VIII, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15468 | Augmentation | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 02/08/2025 | M/S B. ENTERPRISE | 43.57 | 0 | 0 | 0
Total | [13 empty] | 429.32 | 0 | 0