## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HOMRAPOLTA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15471 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 of Augmentation of Homrapolta W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001696/2022-2023 | 11627/AD | 18/02/2023 | 20/03/2023 | TRIMURTI ENTERPRISE | 19.56 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HOMRAPOLTA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15471 | Augmentation | Relaying of damaged DI pipe at Homrapolta W/S Scheme due widening of PMGSY Road by Zilla Parishad under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/002161/2020-2021 | 1593/CSD | 23/02/2021 | 25/03/2021 | ARANYA ENTERPRISE | 3.54 | 3.5 | 98.86 | 99
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HOMRAPOLTA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15471 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 222/AD | 21/04/2023 | 21/04/2023 | Resource Division | 39.74 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HOMRAPOLTA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15471 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000256/2023-2024 | 3048/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.92 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HOMRAPOLTA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15471 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (700 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Homrapolta Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002005/2022-2023 | 12819/AD | 16/03/2023 | 15/05/2023 | TIYASHA ENTERPRISE | 58.34 | 21.27 | 36.47 | 51
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HOMRAPOLTA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15471 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001689/2022-2023 | 11620/AD | 18/02/2023 | 04/04/2023 | B. ENTERPRISE | 7.07 | 6.78 | 95.89 | 98
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF HOMRAPOLTA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15471 | Augmentation | Quotation for new service ( power ) connection at Homrapolta under Canning -II block (REF ID : 106665552) (APP ID: 1007924615) |  |  | BILL/01004/2024-2025 | BP-2024-25-205 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.77 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF HOMRAPOLTA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15471 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Homrapolta water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000287/2023-2024 | 1147/SMD | 24/04/2023 | 05/04/2025 | A.S.ENTERPRISE | 10.9 | 0 | 0 | 95
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF HOMRAPOLTA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15471 | Augmentation | Inter connection and rising main with supply of specials at PH-III of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001080/2023-2024 | 3539/AD | 17/10/2023 | 31/05/2025 | TIYASHA ENTERPRISE | 96.43 | 0 | 0 | 35
Total | [13 empty] | 240.27 | 31.56 | 13.13