## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 117/AD | 13/04/2023 | 13/04/2023 | Resource Division | 0.34 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 219/AD | 21/04/2023 | 21/04/2023 | Resource Division | 159.84 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 841/AD | 27/05/2023 | 27/05/2023 | Resource Division | 1.72 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2 of Augmentation of Kalikatala Zone-I and II water supply scheme under SMD, PHE Dte. Block Canning-II | Assistant Engineer | Junior Engineer | ORD/001917/2023-2024 | 1198/SMD | 22/03/2024 | 20/06/2024 | MAA TARA ENTERPRISE | 11.42 | 0 | 0 | 95
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalikatala W/S Scheme (Zone - I), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001686/2022-2023 | 11493/AD | 15/02/2023 | 01/04/2023 | KUNDU CONSTRUCTION CO. | 7.1 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | : Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalikatala W/S Scheme (Zone - II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001687/2022-2023 | 11494/AD | 15/02/2023 | 01/04/2023 | ARFIN CONSTRUCTION | 7.09 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 for each zone of Augmentation of Kalikatala (Zone - I & II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001695/2022-2023 | 11626/AD | 18/02/2023 | 04/04/2023 | ELECTROMECH | 39.19 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | Inter connection and rising main with supply of specials at PH-IV for each zone of Kalikatala (Zone - I and II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000236/2023-2024 | 1324/AD | 07/07/2023 | 05/09/2023 | JAYANTA KUMAR DEY | 64.08 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | Supply and delivery of submersible pumping machinery for Kalikatala w/s scheme Zone-II PH-1 under SMD PHE Dte. |  |  | ORD/001458/2023-2024 | .1421/SMSD | 21/11/2023 | 06/12/2023 | S.S.G ENTERPRISE | 0.9 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | Quotation for new service ( power ) connection at Kalikatala Zone-II , PH-4 under Canning -II block (REF ID : 106665561) (APP ID: 1007923967) |  |  | BILL/00996/2024-2025 | BP-2024-25-204 | 30/07/2024 | 30/07/2024 | WBSEDCL | 4.82 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/04683/2023-2024 | BP-2023-24-508 | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.28 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15472 | Augmentation | Surging of 03 no. Big dia Tubewell of Ramchadrakhali (Zone-II) (TW-3) and Kalikatala (Zone-II) (TW-1 & 3) W/S Scheme under JJM, Block - Basanti & Canning-II, under Canning Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000242/2025-2026 | 681/CSD | 26/05/2025 | 25/06/2025 | FORTUNE ENGINEERING | 4.3 | 0 | 0 | 0
Total | [13 empty] | 304.09 | 0 | 0