## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Additional work of construction of concrete road from main road to reservoir site of Moukhali W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/001581/2020-2021 | 981/CSD | 09/11/2020 | 29/11/2020 | RIVER BENZ CONSTRUCTION | 1.93 | 0 | 0 | 90
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (449 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Maukhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2023-2024 | 1027/AD | 13/06/2023 | 28/07/2023 | JAMIRUL CONSTRUCTION | 57.91 | 24.74 | 42.72 | 50
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Moukhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 6) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001692/2022-2023 | 11623/AD | 18/02/2023 | 04/04/2023 | SRI DURGA ENTERPRISE | 7.05 | 6.64 | 94.2 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - V & VI of Augmentation of Moukhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001694/2022-2023 | 11625/AD | 18/02/2023 | 04/04/2023 | M/S MARIYA ENTERPRISES | 39.17 | 36.94 | 94.29 | 100
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 & 2 for Augmentation of Moukhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000032/2023-2024 | 982/SMD | 05/04/2023 | 01/08/2026 | BINAPANI ENTERPRISE | 21.57 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Moukhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001691/2022-2023 | 11622/AD | 18/02/2023 | 04/04/2023 | SRI DURGA ENTERPRISE | 7.05 | 6.49 | 92.05 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Moukhali Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002059/2023-2024 | 1305/AD | 04/03/2024 | 03/04/2024 | GANGA TUBEWELL AND HARDWARE | 2.82 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Laying pipe line to connect the uncovered habitation at Moukhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001025/2024-2025 | 4935/AD | 03/12/2024 | 02/01/2025 | KALIDAS ENTERPRISE | 17.41 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 550/AD | 25/01/2024 | 25/01/2024 | Resource Division | 79.87 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Restoration of Jhorer more to Khuribhanga pumping station Road under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division |  |  | BILL/01324/2024-2025 | BP-2024-25-621 | 27/09/2024 | 27/09/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 20.08 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Quotation for new service ( power ) connection at Moukhali , PH-5 under Canning -I block (REF ID : 106673103) (APP ID: 1007938965) |  |  | BILL/01470/2024-2025 | BP-2024-25-365 | 11/09/2024 | 11/09/2024 | WBSEDCL | 9.9 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Quatation for new service (power) connection at Moukhali PH-1 Water supply scheme under Canning-I block Reference ID-106692521, Application No-1007977259 |  |  | BILL/01362/2024-2025 | BP-2024-25-327 | 31/08/2024 | 31/08/2024 | WBSEDCL | 13.36 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Construction of boundary wall at Pump House - 6 at Ground Water Based Augmentation Piped Water Supply Scheme of Moukhali W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002488/2024-2025 | 770/AD | 25/02/2025 | 27/03/2025 | SMART SOLUTION | 6.99 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15473 | Augmentation | Surging of 01 no. Big dia Tubewell of Moukhali (TW-3) W/S Scheme, Block ¿ Canning ¿ I of Canning Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000062/2025-2026 | 542/CSD | 29/04/2025 | 29/05/2025 | S.K.GOLUI | 2.3 | 0 | 0 | 100
Total | [13 empty] | 287.42 | 74.81 | 26.03