## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SINGESHWAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15476 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using UPVC pipe (CD) and UPVC Deep well screen (RDS) pipe with ribs pipe at Tube Well No. - 3 of Augmentation of Singheswar W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001815/2022-2023 | 12155/AD | 01/03/2023 | 15/04/2023 | SNEHA CONSTRUCTION | 19.9 | 18.28 | 91.9 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SINGESHWAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15476 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 226/AD | 24/04/2023 | 24/04/2023 | Resource Division | 23.13 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SINGESHWAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15476 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Singeshwar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000040/2023-2024 | 1000/SMD | 10/04/2023 | 09/07/2023 | A.G.ENTERPRISE | 11.15 | 10.27 | 92.12 | 95
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SINGESHWAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15476 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Singheswar W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001816/2022-2023 | 12156/AD | 01/03/2023 | 15/04/2023 | GHOSH CONSTRUCTION | 7.09 | 7.06 | 99.58 | 96
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SINGESHWAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15476 | Augmentation | Supply & Installation of LED board at PH-1 of Singheswar (Aug) water supply scheme under South 24-Pgs Mechanical Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000109/2024-2025 | 529/SMSD | 29/04/2024 | 14/05/2024 | SOHINI ENTERPRISE | 0.39 | 0.39 | 100 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SINGESHWAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15476 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04034/2023-2024 | BP-2023-24-411 | 13/12/2023 | 13/12/2023 | WBSEDCL | 6.27 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SINGESHWAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15476 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (410 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Singheswar Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002312/2023-2024 | 1065/AD | 21/02/2024 | 29/11/2024 | RAKTIM ENTERPRISE | 35.55 | 0 | 0 | 93
Total | [13 empty] | 103.48 | 36.01 | 34.8