## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15477 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Adhia W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001347/2022-2023 | 10943/AD | 06/02/2023 | 08/03/2023 | SNEHA CONSTRUCTION | 19.49 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15477 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Adhia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000027/2023-2024 | 972/SMD | 04/04/2023 | 03/07/2023 | SUPER SKILL | 11.7 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15477 | Augmentation | Hiring of Diesel Car / Luxury Taxi for official use of Assistant Engineer, Canning Sub-Division, PHE Dte. for the period from 01.03.2023 to 31.08.2023 | Assistant Engineer, Canning sub division |  | ORD/002172/2022-2023 | 1370/CSD | 27/02/2023 | 30/08/2023 | SAILEN CHANDRA DAS | 0.86 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15477 | Augmentation | Bypass arrangement on risingmain, installation of air valve, restoration of damage road & other works at Adhia W/S Scheme,Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001574/2020-2021 | 1062/CSD | 27/11/2020 | 27/12/2020 | SUKANTA HALDER | 1.48 | 0 | 0 | 96
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15477 | Augmentation | Sinking of 300mm x 200mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 of Adhia Water Supply Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2022-2023 | 795/AD | 12/05/2022 | 11/06/2022 | AQUATECH ENGINEERS | 24.68 | 0 | 0 | 62
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15477 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000118/2022-2023 | 3045/AD | 28/09/2023 | 28/09/2023 | Resource Division | 51.93 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15477 | Augmentation | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Canning Sub-Division of Alipore Division, PHE Dte. for 1 (one) Year from the issuance of work order. | Assistant Engineer, Canning sub division |  | ORD/002175/2022-2023 | 1354/CSD | 20/02/2023 | 20/02/2024 | SWAPAN KUMAR MANDAL | 4.8 | 0 | 0 | 12
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15477 | Augmentation | Construction of 400 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing )with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. of Adhia piped water supply scheme of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. [SM/07596 & SM/15477] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000690/2024-2025 | 4271/AD | 28/10/2024 | 25/07/2025 | MAMON ENTERPRISE AND CONSTRUCTION | 128.22 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15477 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000725/2023-2024 | 547/AD | 25/01/2024 | 25/01/2024 | Resource Division | 55.77 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15477 | Augmentation | Hiring of Diesel Car / Luxury Taxi for official use of Assistant Engineer, Canning Sub-Division, PHE Dte. for the period from 01.09.2023 to 29.02.2024 | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001185/2023-2024 | 877/CSD | 31/08/2023 | 29/02/2024 | SAILEN CHANDRA DAS | 0.86 | 0 | 0 | 100
Total | [13 empty] | 299.77 | 0 | 0