## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15478 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kaluagachi W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001683/2022-2023 | 11490/AD | 15/02/2023 | 01/04/2023 | R CONSTRUCTION | 7.11 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15478 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 for each zone of Augmentation of Kalugachi W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001770/2022-2023 | 12043/AD | 27/02/2023 | 29/03/2023 | ZINARUL ISLAM | 19.59 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15478 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 of Kalugachi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000035/2023-2024 | 985/SMD | 05/04/2023 | 04/07/2023 | SUDIP PRADHAN | 11.18 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15478 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalugachi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000334/2023-2024 | 1551/AD | 17/07/2023 | 28/03/2026 | M/S. MIHIR KUMAR NASKAR | 122.86 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15478 | Augmentation | Additional work for laying distribution in connection with FHTC work at AUGMENTATION AND RETROFITTING OF KALUGACHHI W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (SM/15478) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001016/2023-2024 | 3301/AD | 07/10/2023 | 06/11/2023 | STAR ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 10.97 | 7.41 | 67.49 | 90
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15478 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 116/AD | 13/04/2023 | 13/04/2023 | Resource Division | 0.34 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15478 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2023-2024 | 850/AD | 27/05/2023 | 27/05/2023 | Resource Division | 1.72 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15478 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000262/2023-2024 | 3052/AD | 28/09/2023 | 28/09/2023 | Resource Division | 85.12 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15478 | Augmentation | Additional work inter connection & distribution at Kalugachi W/S Scheme, Block- Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000350/2024-2025 | 722/CSD | 27/06/2024 | 27/07/2024 | P.S. CONSTRUCTION | 2.26 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15478 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kalugachi W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000286/2024-2025 | 2657/AD | 21/06/2024 | 05/08/2024 | RABIUL GAZI | 7.07 | 0 | 0 | 0
Total | [13 empty] | 268.23 | 7.41 | 2.76