## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI | SM/15479 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all the households in Chaplarkhop Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division |  | ORD/000512/2020-2021 | 5127/AD | 08/02/2021 | 08/02/2022 | M/S. DAS BUILDERS | 53.21 | 0 | 0 | 96
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI | SM/15479 | Augmentation | Inter connection between OHR and Distrubtion system with supply of Specials, Laying HDPE pipe, Restoration at Zone - XIII water supply scheme of Mathurapur - II Block (Chaplarkhop PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002230/2023-2024 | 922/AD | 08/02/2024 | 09/03/2024 | SUKUMAR HALDAR | 7.81 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI | SM/15479 | Augmentation | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XIII, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001962/2022-2023 | 12716/AD | 14/03/2023 | 13/04/2023 | P.L.CONSTRUCTION | 25.31 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI | SM/15479 | Augmentation | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Head Work Site) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Chaplarkhop W/S Scheme (Zone-XIII, Mathurapur-II Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000431/2023-2024 | 1919/AD | 01/08/2023 | 31/08/2023 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 19.83 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI | SM/15479 | Augmentation | Repairing of pump house 2 and approach road and plinth protection including boundary wall at Chaplarkhop W/S Scheme, modified as Zone- XIII of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001711/2023-2024 | 301/RSD | 29/09/2023 | 28/11/2023 | HALDER ENTERPRISE (I) | 2.86 | 0 | 0 | 90
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI | SM/15479 | Augmentation | Construction of boundary wall at Zone - XIII, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface Water Based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001866/2023-2024 | 140/AD | 05/01/2024 | 04/02/2024 | SUKUMAR HALDAR | 8.63 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI | SM/15479 | Augmentation | Extention of pipeline for Providing Functional Household Tap Connection (FHTC) and allied works at Zone-XIII, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. |  | Junior Engineer 2, Raidghi Sub Division,Junior Engineer1, Raidghi Sub Division | ORD/000609/2024-2025 | 749/RSD | 03/10/2024 | 02/12/2024 | P.L.CONSTRUCTION | 3.03 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI | SM/15479 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XIII, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (New FHTC = 83 Nos.) |  | Junior Engineer 2, Raidghi Sub Division,Junior Engineer1, Raidghi Sub Division | ORD/000610/2024-2025 | 750/RSD | 03/10/2024 | 02/12/2024 | P.L.CONSTRUCTION | 4.2 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI | SM/15479 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000660/2023-2024 | 264/AD | 15/01/2024 | 15/01/2024 | Resource Division | 1.69 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI | SM/15479 | Augmentation | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 21/07/2025 | L.N. ENTERPRISE | 27.53 | 0 | 0 | 0
Total | [13 empty] | 154.12 | 0 | 0