## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15491 | Augmentation | Laying of distribution pipeline of Zone- XI at Mathurapur - II Block under MEGA SURFACE WATER BASED WATER SUPPLY SCHEME, FALTA-MATHURAPUR, South 24 Parganas by remodeling the existing Nandakumarpur Zone-II water supply scheme under Raidighi Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001727/2020-2021 | 5316/AD | 18/02/2021 | 18/06/2021 | M/S B.N.ENTERPRISE | 73.83 | 4.22 | 5.71 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15491 | Augmentation | Functional Household Tap Connection (FHTC) to the households at Marayari Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part- II) | Assistant Engineer, Raidighi sub division |  | ORD/000580/2020-2021 | 506/RSD | 24/12/2020 | 22/02/2021 | TIYASHA ENTERPRISE | 4.82 | 4.48 | 92.92 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15491 | Augmentation | Functional Household Tap Connection (FHTC) to the households at Janar Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part-II) | Assistant Engineer, Raidighi sub division |  | ORD/000359/2020-2021 | 426/RSD | 23/11/2020 | 22/01/2021 | TIYASHA ENTERPRISE | 4.82 | 1.14 | 23.55 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15491 | Augmentation | Special repairing work of pipeline under Nandakumarpur Zone -II of Nandakumarpur W/S Scheme, Mathurapur -II Block under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/002182/2020-2021 | 709/RSD | 08/02/2021 | 09/04/2021 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.04 | 3.75 | 92.77 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15491 | Augmentation | Dismantling and restoration of concrete village road for laying pipe line work at Zone-XI of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000222/2022-2023 | 3063/AD | 13/07/2022 | 12/08/2022 | M/S B.N.ENTERPRISE | 6.13 | 6.07 | 99 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15491 | Augmentation | Providing FHTC including laying distribution system and other allied works at Zone- XI of Mathurapur -II Block for ''Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer1, Raidghi Sub Division | ORD/000088/2023-2024 | 499/AD | 11/05/2023 | 02/02/2025 | M/S B.N.ENTERPRISE | 131.92 | 72.83 | 55.21 | 60
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15491 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000654/2023-2024 | 258/AD | 15/01/2024 | 15/01/2024 | Resource Division | 5.13 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15491 | Augmentation | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 21/07/2025 | L.N. ENTERPRISE | 27.53 | 0 | 0 | 0
Total | [13 empty] | 258.22 | 92.48 | 35.81