## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-IX, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15492 | Augmentation | EARNEST MONEY DEDUCTION. |  |  | ORD/002114/2019-2020 | 7761/AD | 27/02/2020 | 27/02/2025 | G.B. CONSTRUCTION & CO. | 23.06 | 23.06 | 100 | 5
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-IX, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15492 | Augmentation | Supply and delivery at site of different dia. Specials in connection with Interconnection of Tube Well at Zone - IX (Nagendrapur PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000613/2023-2024 | 243/RSD | 22/08/2023 | 21/09/2023 | JAL PRAVAHIKA PVT. LTD. | 2.34 | 2.34 | 100 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-IX, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15492 | Augmentation | Supply and delivery at site of different dia. Specials in connection with laying distribution system of piped water supply at Zone - IX (Nagendrapur PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000610/2023-2024 | 241/RSD | 22/08/2023 | 21/09/2023 | JAL PRAVAHIKA PVT. LTD. | 4.04 | 4.04 | 100 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-IX, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15492 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000662/2023-2024 | 266/AD | 15/01/2024 | 15/01/2024 | Resource Division | 8.13 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-IX, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15492 | Augmentation | Providing FHTC including distribution system and other allied works at Zone- IX of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000085/2023-2024 | 213/AD | 20/04/2023 | 08/07/2025 | JAL PRAVAHIKA PVT. LTD. | 144.19 | 36.11 | 25.04 | 30
Total | [13 empty] | 181.75 | 65.55 | 36.06