## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15493 | Augmentation | Laying of Rising Main (From 2nd Tube Well to Over Head Reservoir) and construction of valve chamber of piped water supply at Zone - XII of Mathurapur - I Block (Abad Bhagabanpur PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000248/2023-2024 | 185/RSD | 14/07/2023 | 13/08/2023 | SUKUMAR HALDAR | 3.78 | 3.75 | 99.17 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15493 | Augmentation | Remodeling of distribution system for providing Functional Household Tap Connection (FHTC) to all the households in Zone-XII of Mathurapur-I Block including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water based water supply scheme for Falta-Mathurapur, District-South 24-Parganas" under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000115/2022-2023 | 1660/AD | 10/06/2022 | 08/10/2022 | M/S. SUMAN ENTERPRISE | 236.89 | 142.98 | 60.36 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15493 | Augmentation | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XII, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001959/2022-2023 | 12713/AD | 14/03/2023 | 28/04/2023 | ADITYA HAZRA | 83.94 | 48.15 | 57.37 | 65
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15493 | Augmentation | Repair and renovation work for 250 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir at Abad Bhagabanpur W/S Scheme, modified as Zone- XII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001913/2023-2024 | 143/AD | 05/01/2024 | 19/02/2024 | MAHALAXMI CONSTRUCTION | 16.13 | 0 | 0 | 98
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15493 | Augmentation | Repairing of pump house 1 and approach road and plinth protection including boundary wall at Abad Bhagabanpur W/S Scheme, modified as Zone- XII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001007/2023-2024 | 298/RSD | 29/09/2023 | 28/11/2023 | M/S. GANGA ENTERPRISE | 4.08 | 3.18 | 77.86 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15493 | Augmentation | Extension of pipelines to provide FHTC of Abad Bhagabanpur (Mouza - Ramchandrapur) piped water supply Scheme at Zone- XII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001175/2023-2024 | 354/RSD | 21/11/2023 | 20/01/2024 | S.S. ENTERPRISE (II) | 4.02 | 4.01 | 99.89 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15493 | Augmentation | Extension of pipelines to provide FHTC of Abad Bhagabanpur (Mouza - Satpukur, Rajarampur, Chakbhagabanpur, Nandapur) piped water supply Scheme at Zone- XII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001176/2023-2024 | 355/RSD | 21/11/2023 | 20/01/2024 | M/S. SUMAN ENTERPRISE | 4.68 | 2.18 | 46.65 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15493 | Augmentation | Extension of pipelines to provide FHTC of Abad Bhagabanpur (Mouza - Gadberia) piped water supply Scheme at Zone- XII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001177/2023-2024 | 356/RSD | 21/11/2023 | 20/01/2024 | M/S B ENTERPRISE | 4.7 | 4.69 | 99.93 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15493 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000635/2023-2024 | 239/AD | 15/01/2024 | 15/01/2024 | Resource Division | 4.07 | 0 | 0 | 0
Total | [13 empty] | 362.29 | 208.96 | 57.68