## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15494 | Augmentation | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Goalar Mal (Part-A) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/002365/2020-2021 | 737/RSD | 12/02/2021 | 13/04/2021 | DIBYENDU BHATTACHARYA | 4.82 | 4.32 | 89.59 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15494 | Augmentation | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghatbakultala (Node No. 13-12-10-8) under Ghatbakultala water supply scheme ( Zone-XIII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001547/2021-2022 | 713/RSD | 02/03/2022 | 01/05/2022 | SHEKHAR CHAKRABORTY | 4.79 | 4.79 | 100 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15494 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-H) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000042/2022-2023 | 34/RSD | 19/04/2022 | 18/06/2022 | B.S. CONSTRUCTION | 4.76 | 4.76 | 100 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15494 | Augmentation | Extension of distribution system (Node No. 85-AB) of Ghatbakultala W/S scheme at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000037/2022-2023 | 06/RSD | 04/04/2022 | 03/06/2022 | R.G. ENTERPRISE (I) | 4.72 | 4.77 | 100.89 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15494 | Augmentation | Laying distribution system of piped water supply at Zone- XIII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (PART -A) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000114/2023-2024 | 483/AD | 10/05/2023 | 09/06/2023 | SUTAPA ENTERPRISE | 16.05 | 12.28 | 76.51 | 98
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15494 | Augmentation | Laying distribution system of piped water supply at Zone- XIII of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001040/2024-2025 | 4958/AD | 04/12/2024 | 02/02/2025 | SUKUMAR HALDAR | 31.88 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15494 | Augmentation | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XIII, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001967/2022-2023 | 12721/AD | 14/03/2023 | 13/04/2023 | THE TOWER CONSTRUCTION | 39.69 | 39.48 | 99.48 | 60
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15494 | Augmentation | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Ghatbakultala W/S Scheme (Zone-XIII, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000434/2023-2024 | 1922/AD | 01/08/2023 | 31/08/2023 | ALISHA ENTERPRISE | 19.83 | 18.73 | 94.45 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15494 | Augmentation | Repairing of pump house no.2, including boundary wall and approach road and plinth protection at Ghatbakultala W/S Scheme, modified as Zone- XIII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000608/2024-2025 | 748/RSD | 03/10/2024 | 02/12/2024 | M/S. GANGA ENTERPRISE | 4.74 | 4.66 | 98.31 | 95
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15494 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000602/2023-2024 | 230/AD | 11/01/2024 | 11/01/2024 | Resource Division | 2.56 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/15494 | Augmentation | Interconnection with OHR, Rising main and distribution system for different Zones ( Zone-II, V, XIII), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000109/2025-2026 | 2575/AD | 03/06/2025 | 02/08/2025 | SOURAV DEBNATH | 15.09 | 0 | 0 | 0
Total | [13 empty] | 148.93 | 93.78 | 62.97