## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-X, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15495 | Augmentation | Horizontal boring and allied works for laying of distribution system of piped water supply at Zone-X of Mathurapur-II Block for ?Mega Surface water based water supply scheme for Falta- Mathurapur, District South 24 parganas? under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001771/2021-2022 | 629/RSD | 29/12/2021 | 13/01/2022 | M/S B.M. CONSTRUCTION | 3 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-X, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15495 | Augmentation | Repairing of pump house - 1 and 2, including boundary wall and approach road and plinth protection at Nandakumarpur Zone - I W/S Scheme, modified as Zone- X of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001300/2024-2025 | 5374/AD | 23/12/2024 | 22/01/2025 | MONDAL ENTERPRISE (JOYNAGAR) | 4.85 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-X, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15495 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000656/2023-2024 | 260/AD | 15/01/2024 | 15/01/2024 | Resource Division | 3.84 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-X, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15495 | Augmentation | Providing FHTC including distribution system and other allied works at Zone- X of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer1, Raidghi Sub Division | ORD/000355/2023-2024 | 3733/AD | 03/11/2023 | 25/10/2025 | M/S ASCON | 111.11 | 0 | 0 | 50
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-X, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15495 | Augmentation | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 21/07/2025 | L.N. ENTERPRISE | 27.53 | 0 | 0 | 0
Total | [13 empty] | 150.34 | 0 | 0