## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System under Zone-VIII, Mathurapur-II Block by Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta | SM/15497 | Augmentation | Restoration of Pipeline (N.P. 70-71, 80-81) at Purba Jatardeul mouza under Purba Jatardeul Water supply Scheme of Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division,Assistant Engineer, Raidighi sub division |  | ORD/001770/2021-2022 | 628/RSD | 29/12/2021 | 13/01/2022 | NITYANANDA MONDAL | 2 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System under Zone-VIII, Mathurapur-II Block by Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta | SM/15497 | Augmentation | Providing FHTC including distribution system and other allied works at Zone- VIII of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000044/2023-2024 | 179/AD | 19/04/2023 | 18/06/2023 | G.B. CONSTRUCTION & CO. | 100.29 | 0 | 0 | 25
3 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System under Zone-VIII, Mathurapur-II Block by Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta | SM/15497 | Augmentation | Rejuvenation of Functional Household Tap Connection (FHTC) at Zone - VIII (Paschim Jatardule) of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002276/2023-2024 | 483/RSD | 15/02/2024 | 15/04/2024 | G.B. CONSTRUCTION & CO. | 4.78 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System under Zone-VIII, Mathurapur-II Block by Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta | SM/15497 | Augmentation | Laying distribution system of piped water supply at Zone- VIII of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001043/2024-2025 | 4960/AD | 04/12/2024 | 02/02/2025 | TIYASHA ENTERPRISE | 28.21 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System under Zone-VIII, Mathurapur-II Block by Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta | SM/15497 | Augmentation | Rejuvenation of distribution pipe line and other allied works to Providing Functional Household Tap Connection (FHTC) at Zone- VIII of Mathurapur -II Block in connection with Jal Jeevan Mission (JJM) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002274/2023-2024 | 481/RSD | 15/02/2024 | 15/04/2024 | M/S KALPANA CONSTRUCTION | 2.4 | 0 | 0 | 98
6 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System under Zone-VIII, Mathurapur-II Block by Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta | SM/15497 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000661/2023-2024 | 265/AD | 15/01/2024 | 15/01/2024 | Resource Division | 5.21 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System under Zone-VIII, Mathurapur-II Block by Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta | SM/15497 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all the households in Purba Jatardeul Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000511/2020-2021 | 5196/AD | 12/02/2021 | 12/02/2022 | G.B. CONSTRUCTION & CO. | 125.27 | 0 | 0 | 98
8 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System under Zone-VIII, Mathurapur-II Block by Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta | SM/15497 | Augmentation | Rejuvenation of Functional Household Tap Connection (FHTC) at Zone - VIII (Purba Jatardule) of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002275/2023-2024 | 482/RSD | 15/02/2024 | 15/06/2024 | G.B. CONSTRUCTION & CO. | 4.78 | 0 | 0 | 98
Total | [13 empty] | 272.95 | 0 | 0