## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - V, VI & VII of Augmentation of Bijoynagar W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001771/2022-2023 | 12044/AD | 27/02/2023 | 28/04/2023 | ZINARUL ISLAM | 65.93 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bijoynagar W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 7) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001716/2022-2023 | 11680/AD | 20/02/2023 | 06/04/2023 | S.B. ENTERPRISE | 8.61 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Inter connection and rising main with supply of specials at PH-V, VI & VII of Bijoynagar W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000242/2023-2024 | 1394/AD | 12/07/2023 | 11/08/2023 | ISHAN CONSTRUCTION | 54.94 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Bijoynagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000043/2023-2024 | 1039/SND | 17/04/2023 | 16/07/2023 | PADMA ENGINEERING CO. | 33.61 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2022-2023 | 383/AD | 02/05/2023 | 02/05/2023 | Resource Division | 99.35 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Protection of pipe line and other allied works at Augmentation of Bijoynagar W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000752/2024-2025 | 4426/AD | 05/11/2024 | 04/01/2025 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 93.79 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Protection of pipe line and other allied works at Augmentation of Bijoynagar W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001060/2024-2025 | 1288/CSD | 20/11/2024 | 20/12/2024 | A.P. CONSTRUCTION | 4.55 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Augmentation of Bijoynagar piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. (SM/15499) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001099/2024-2025 | 5030/AD | 06/12/2024 | 02/09/2025 | UNITED BUILDERS | 195.23 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Construction of boundary wall at Pump House No. - 5 for Ground Water Based at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001241/2024-2025 | 5222/AD | 16/12/2024 | 15/01/2025 | MAA SANTOSHI ENTERPRISE | 15.05 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Quotation for new service( power) connection at Bijoynagar PH-2 Water supply scheme under Gosaba block. Reference ID:-106770519, Application No :-1008125182 |  |  | BILL/01846/2024-2025 | BP-2024-25-468 | 18/11/2024 | 18/11/2024 | WBSEDCL | 8 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Quotation for new service( power) connection at Bijoynagar ( TW-1) Water supply scheme under Gosaba block. Reference ID:-106770522, Application No :-1008125225 |  |  | BILL/01842/2024-2025 | BP-2024-25-467 | 18/11/2024 | 18/11/2024 | WBSEDCL | 3.92 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bijoynagar W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 6) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001699/2022-2023 | 11663/AD | 20/02/2023 | 06/04/2023 | ESSCON | 8.61 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bijoynagar W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001715/2022-2023 | 11679/AD | 20/02/2023 | 01/02/2025 | JYOTI ENTERPRISES | 8.4 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Construction of boundary wall at Pump House No. - 7 at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000022/2025-2026 | 2008/AD | 28/04/2025 | 28/05/2025 | RAHIMA ENTERPRISE | 11.92 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15499 | Augmentation | Construction of boundary wall at Pump House No. - 6 at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000023/2025-2026 | 2009/AD | 28/04/2025 | 28/05/2025 | RAHIMA ENTERPRISE | 11.49 | 0 | 0 | 0
Total | [13 empty] | 623.39 | 0 | 0