## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Laying pipe line to connect the uncovered habitations at Banibadabelekhali Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001061/2021-2022 | 5296/AD | 04/01/2022 | 05/03/2022 | S.S. ENTERPRISE (I) | 63.28 | 41.64 | 65.8 | 81
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - V of Augmentation of Banibadabelekhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001808/2022-2023 | 12132/AD | 01/03/2023 | 31/03/2023 | KUNTAL CHOWDHURY | 19.59 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Banibadabelekhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH No. - 5) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002050/2022-2023 | 13050/AD | 24/03/2023 | 08/05/2023 | BINAPANI ENTERPRISE | 7.09 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Banibada Belekhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 974/SMD | 04/04/2023 | 03/07/2023 | SUPER SKILL | 10.76 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Laying of pipe line due to widening of roads from P.C. Sen Road (Raibaghini) to Golabari Kheyaghat at Banibadabelekhali Water Supply Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000030/2022-2023 | 516/AD | 25/04/2022 | 25/05/2022 | M.T.C. CONSTRUCTION | 46.43 | 46.39 | 99.93 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Rising main with OHR to distribution system at Banibadabelekhali W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000271/2022-2023 | 263/CSD | 19/05/2022 | 18/06/2022 | R.P. ENTERPRISE | 1.88 | 1.62 | 86.13 | 87
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000119/2022-2023 | 3046/AD | 28/09/2023 | 28/09/2023 | Resource Division | 46.38 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Banibadabelekhali Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001945/2022-2023 | 11505/AD | 15/02/2023 | 01/04/2023 | M/S. MIHIR KUMAR NASKAR | 1.75 | 1.75 | 100 | 95
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000729/2023-2024 | 552/AD | 25/01/2024 | 25/01/2024 | Resource Division | 59.7 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Payment for "Restoration of P.C Sen road Raibaghini to Golabari Kheyaghat(WB/02/ 564) damaged caused due to laying of water pipelines by PHED. |  |  | BILL/01192/2024-2025 | BP-2024-25-556 | 11/09/2024 | 11/09/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 21 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Quatation for new service (power) connection at Banibada belekhali PH-1 Water supply scheme under Canning-I block Reference ID-106692516, Application No-1007977167 |  |  | BILL/01364/2024-2025 | BP-2024-25-326 | 31/08/2024 | 31/08/2024 | WBSEDCL | 14.77 | 0 | 0 | 0
Total | [13 empty] | 292.63 | 91.4 | 31.23