## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Laying pipe line to connect the uncovered habitations at Banibadabelekhali Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001061/2021-2022 | 5296/AD | 04/01/2022 | 05/03/2022 | S.S. ENTERPRISE (I) | 63.28 | 0 | 0 | 81
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - V of Augmentation of Banibadabelekhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001808/2022-2023 | 12132/AD | 01/03/2023 | 31/03/2023 | KUNTAL CHOWDHURY | 19.59 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Banibadabelekhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH No. - 5) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002050/2022-2023 | 13050/AD | 24/03/2023 | 08/05/2023 | BINAPANI ENTERPRISE | 7.09 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Banibada Belekhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 974/SMD | 04/04/2023 | 03/07/2023 | SUPER SKILL | 10.76 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Laying of pipe line due to widening of roads from P.C. Sen Road (Raibaghini) to Golabari Kheyaghat at Banibadabelekhali Water Supply Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000030/2022-2023 | 516/AD | 25/04/2022 | 25/05/2022 | M.T.C. CONSTRUCTION | 46.43 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Rising main with OHR to distribution system at Banibadabelekhali W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000271/2022-2023 | 263/CSD | 19/05/2022 | 18/06/2022 | R.P. ENTERPRISE | 1.88 | 0 | 0 | 87
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000119/2022-2023 | 3046/AD | 28/09/2023 | 28/09/2023 | Resource Division | 46.38 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (755 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) of Augmentation of Banibadabelekhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000221/2023-2024 | 1026/AD | 13/06/2023 | 02/06/2025 | M.T.C. CONSTRUCTION | 58.43 | 0 | 0 | 35
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Banibadabelekhali Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001945/2022-2023 | 11505/AD | 15/02/2023 | 01/04/2023 | M/S. MIHIR KUMAR NASKAR | 1.75 | 0 | 0 | 95
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000729/2023-2024 | 552/AD | 25/01/2024 | 25/01/2024 | Resource Division | 59.7 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Payment for "Restoration of P.C Sen road Raibaghini to Golabari Kheyaghat(WB/02/ 564) damaged caused due to laying of water pipelines by PHED. |  |  | BILL/01192/2024-2025 | BP-2024-25-556 | 11/09/2024 | 11/09/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 21 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15500 | Augmentation | Quatation for new service (power) connection at Banibada belekhali PH-1 Water supply scheme under Canning-I block Reference ID-106692516, Application No-1007977167 |  |  | BILL/01364/2024-2025 | BP-2024-25-326 | 31/08/2024 | 31/08/2024 | WBSEDCL | 14.77 | 0 | 0 | 0
Total | [13 empty] | 351.07 | 0 | 0