## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15502 | Augmentation | Laying pipe line to connect the uncovered habitation (Mondal Para) at Bhaleya Mouza of Bhaleya W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/002314/2020-2021 | 1520/CSD | 10/02/2021 | 12/03/2021 | ADITYA SARDAR | 4.83 | 4.64 | 96.16 | 83
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15502 | Augmentation | Laying pipe line to connect the uncovered habitations at Mouza-Baluijhaka and Bhaleya of Bhaleya Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001065/2021-2022 | 5300/AD | 04/01/2022 | 05/03/2022 | M/S CHANDIMATA CONSTRUCTION | 33.22 | 32.44 | 97.64 | 98
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15502 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bhaleya W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001708/2022-2023 | 11672/AD | 20/02/2023 | 06/04/2023 | R.G. ENTERPRISE (I) | 7.07 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15502 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bhaleya W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001707/2022-2023 | 11671/AD | 20/02/2023 | 06/04/2023 | BARUN KANTI PAUL | 7.09 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15502 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 & 5 of Augmentation of Bhaleya W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001813/2022-2023 | 12153/AD | 01/03/2023 | 15/04/2023 | M.R.ENTERPRISE (II) | 39.03 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15502 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 & 2 for Augmentation of Bhaleya water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000028/2023-2024 | 973/SMD | 04/04/2023 | 03/07/2023 | ORIENTAL ENGINEERING CO. | 23.45 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15502 | Augmentation | Interconnection & rising main with supply of specials from Head work site to PH-IV & Head work site to PH-V of Bhaleya W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000321/2023-2024 | 1547/AD | 17/07/2023 | 25/06/2025 | SANKAR MONDAL | 132.1 | 92.97 | 70.38 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15502 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Bhaleya Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001944/2022-2023 | 11504/AD | 15/02/2023 | 01/04/2023 | M/S. M.K. NASKAR & CONSTRUCTION | 2.6 | 2.6 | 100 | 95
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15502 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000249/2023-2024 | 3039/AD | 28/09/2023 | 28/09/2023 | Resource Division | 81.05 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15502 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000727/2023-2024 | 549/AD | 25/01/2024 | 25/01/2024 | Resource Division | 111.53 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15502 | Augmentation | Quotation for new service ( power ) connection at Bhaleya PH-4 under Canning -I block (REF ID : 106692525) (APP ID: 1007977420) |  |  | BILL/01366/2024-2025 | BP-2024-25-325 | 31/08/2024 | 31/08/2024 | WBSEDCL | 6.44 | 0 | 0 | 0
Total | [13 empty] | 448.42 | 132.65 | 29.58