## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Inter connection and rising main with supply of specials from Head work site to PH-IV and Head work site to PH-V of Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/002001/2022-2023 | 12815/AD | 16/03/2023 | 30/04/2023 | SUNNY CONSTRUCTION | 46.05 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000117/2022-2023 | 3056/AD | 28/09/2023 | 28/09/2023 | Resource Division | 97.75 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03413/2023-2024 | BP-2023-24-373 | 13/11/2023 | 13/11/2023 | WBSEDCL | 14.74 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Bharatgarh water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/000017/2023-2024 | 952/SMD | 04/04/2023 | 03/06/2025 | SHIVAM ENTERPRISE | 23.39 | 0 | 0 | 30
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 & 5 of Augmentation of Bharatgarh W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001814/2022-2023 | 12154/AD | 01/03/2023 | 15/04/2023 | B.K. ENTERPRISE. | 39.96 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001714/2022-2023 | 11678/AD | 20/02/2023 | 06/04/2023 | JYOTI ENTERPRISES | 6.93 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Bharatgarh Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001947/2022-2023 | 11506/AD | 15/02/2023 | 01/04/2023 | GANGA TUBEWELL AND HARDWARE | 2.07 | 0 | 0 | 95
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Bharatgarh W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001193/2023-2024 | 3998/AD | 21/11/2023 | 21/12/2023 | MEHAI TECHNOLOGY LIMITED | 19.99 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Restoration of Basanti Herobhanga Road from 0.00 kmp to 19.95km. block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division |  |  | BILL/01321/2024-2025 | BP-2024-25-683 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 107.4 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Charges for new service connection at pump house no 4 of Bharatghar water supply scheme (Basanti Block) |  |  | BILL/01523/2024-2025 | BP-2024-25-364 | 11/09/2024 | 11/09/2024 | WBSEDCL | 13.71 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Payment for "Restoration of L066-Sibganj To Nol Garanbose Kheyaghat Via Maheshpur H S nd Bharatgarh Market(WB/02/318), damaged caused due to laying of water pipelines by PHED. |  |  | BILL/01191/2024-2025 | BP-2024-25-557 | 11/09/2024 | 11/09/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 25.5 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001713/2022-2023 | 11677/AD | 20/02/2023 | 10/05/2025 | R.G. ENTERPRISE (I) | 7.1 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (550 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Bharatgarh Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001998/2022-2023 | 12812/AD | 16/03/2023 | 18/07/2025 | M/S. MIHIR KUMAR NASKAR | 46.27 | 0 | 0 | 30
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Bharatghar W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15503) | Assistant Engineer | Junior Engineer | ORD/000920/2025-2026 | 683/SMSD | 15/05/2025 | 30/05/2025 | SHIVAM ENTERPRISE | 0.58 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Bharatghar W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15503) | Assistant Engineer | Junior Engineer | ORD/000921/2025-2026 | 684/SMSD | 15/05/2025 | 30/05/2025 | SHIVAM ENTERPRISE | 0.91 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15503 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Bharatghar W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15503) | Assistant Engineer | Junior Engineer | ORD/000922/2025-2026 | 685/SMSD | 15/05/2025 | 30/05/2025 | SHIVAM ENTERPRISE | 0.91 | 0 | 0 | 100
Total | [13 empty] | 453.27 | 0 | 0