## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-III, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15504 | Augmentation | Inter connection between tubewells and Rising Main system of piped water supply at Zone - III of Mathurapur - II Block (Koutala PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001969/2022-2023 | 12723/AD | 14/03/2023 | 13/04/2023 | NITYANANDA MONDAL | 17.09 | 16.18 | 94.67 | 95
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-III, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15504 | Augmentation | Construction of 450 cum. Capacity 20mtr. staging height RCC Over Head Reservoir at as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Mathurapur-II block (zone-III) for Mega surface water based water supply Scheme for Falta Mathurapur, South 24 Parganas under AD PHE Dte. | Assistant Engineer, Raidighi sub division |  | ORD/002154/2019-2020 | 7936/AD | 11/03/2020 | 10/03/2025 | PIKASU BOSE | 23.76 | 23.76 | 100 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-III, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15504 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000648/2023-2024 | 251/AD | 15/01/2024 |  | Resource Division | 4.97 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-III, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15504 | Augmentation | Repairing of boundary wall at Koutala W/S Scheme, modified as Zone- III of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000991/2023-2024 | 287/RSD | 29/09/2023 | 28/11/2023 | M/S R.K.ENTERPRISE | 4.76 | 2.31 | 48.43 | 100
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-III, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15504 | Augmentation | Repairing of pump house 2 & 3 and approach road and plinth protection at Koutala W/S Scheme, modified as Zone- III of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000990/2023-2024 | 286/RSD | 29/09/2023 | 28/11/2023 | L.N. ENTERPRISE | 3.48 | 1.67 | 48.11 | 100
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-III, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15504 | Augmentation | Laying distribution system of damaged pipe line of Koutala piped water supply scheme at Zone- III of Mathurapur -II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002375/2023-2024 | 1215/AD | 29/02/2024 | 14/04/2024 | KALIDAS ENTERPRISE | 13.5 | 4.84 | 35.87 | 100
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-III, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15504 | Augmentation | Supply and delivery at site of different dia. Specials in connection with laying distribution system and Rising Main system of piped water supply at Zone - III (Koutala PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle.,Junior Engineer1, Raidghi Sub Division | ORD/000277/2024-2025 | 2473/AD | 14/06/2024 | 04/07/2024 | NITYANANDA MONDAL | 7.42 | 6.63 | 89.29 | 90
8 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-III, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | SM/15504 | Augmentation | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-III, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (New FHTC = 807 Nos.) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000117/2023-2024 | 486/AD | 10/05/2023 | 24/06/2023 | M/S B.M. CONSTRUCTION | 96.3 | 48.37 | 50.23 | 40
Total | [13 empty] | 171.28 | 103.76 | 60.58