## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XIV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER | SM/15506 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000245/2023-2024 | 3066/AD | 28/09/2023 | 28/09/2023 | Resource Division | 39.42 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XIV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER | SM/15506 | Augmentation | Construction of 300 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system, boundary wall and other allied works at Zone- XIV of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer-1, South 24 WS Circle. | ORD/000346/2023-2024 | 1606/AD | 18/07/2023 | 26/01/2026 | A.K. INDUSTRIES | 308.36 | 0 | 0 | 20
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XIV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER | SM/15506 | Augmentation | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 21/07/2025 | L.N. ENTERPRISE | 27.53 | 0 | 0 | 0
Total | [13 empty] | 375.31 | 0 | 0