## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Madhabnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000390/2022-2023 | 3792/SMD | 29/12/2022 | 22/05/2028 | WESTERN ENGINEERING CO. | 23.46 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar Zone -I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =820] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001826/2022-2023 | 12122/AD | 01/03/2023 | 29/06/2023 | KALPANA BUILDERS (I) | 149.55 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar, Zone -I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001779/2022-2023 | 11503/AD | 15/02/2023 | 13/05/2026 | JOY GURU TRADING | 15.14 | 0 | 0 | 60
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Madhabnagar Zone - I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001782/2022-2023 | 11924/AD | 24/02/2023 | 09/06/2026 | M/S. JHARNA ENTERPRISE | 62.67 | 0 | 0 | 30
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Madhabnagar Zone-I W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000153/2023-2024 | 639/AD | 17/05/2023 | 01/07/2023 | M/S PAUL & CO. | 28.77 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of foundation after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Madhabnagar (Zone-I) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000767/2023-2024 | 2929/AD | 21/09/2023 | 17/07/2024 | VISHAL CONSTRUCTION CO. | 590.16 | 45.52 | 7.71 | 45
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Madhabnagar (Zone-I) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001780/2022-2023 | 11757/AD | 21/02/2023 | 07/04/2023 | S. CHAKRABORTY AND CO. | 36.7 | 33.36 | 90.89 | 50
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0.16 | 16.66 | 100
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 533/AD | 12/05/2023 | 12/05/2023 | Resource Division | 17.51 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Material Requisition To Resource Division |  |  | RTOR000522/2023-2024 | 4936/AD | 22/12/2023 | 22/12/2023 | Resource Division | 28.55 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03420/2023-2024 | BP-2023-24-372 | 13/11/2023 | 13/11/2023 | WBSEDCL | 5.92 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Madhabnagar Zone-I PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002606/2023-2024 | 292/KSD | 07/02/2024 | 12/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Material Requisition To Resource Division |  |  | RTOR000580/2023-2024 | 55/AD | 03/01/2024 | 03/01/2024 | Resource Division | 0.18 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Material Requisition To Resource Division |  |  | RTOR000945/2023-2024 | 1679/AD | 22/03/2024 | 22/03/2024 | Resource Division | 27 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Payment for New Service connection of Madhabnagar PH-1, Zone-I W/S Scheme Application No- 1007523052 Reference ID:- 106465635 |  |  | BILL/02223/2024-2025 | BP-2024-25-502 | 19/12/2024 | 19/12/2024 | WBSEDCL | 6.01 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Payment for New Service connection of Madhabnagar PH-2, Zone-I W/S Scheme Application No- 1007523116 Reference ID:- 106465710 |  |  | BILL/02224/2024-2025 | BP-2024-25-503 | 19/12/2024 | 19/12/2024 | WBSEDCL | 6.4 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gopalnagar Uttar PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13870) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000233/2024-2025 | 822/AD | 27/02/2025 | 13/04/2025 | RELIABLE CONSTRUCTIONS | 64.65 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Madhavnagar Zone-1 PWSS, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/15525) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002852/2024-2025 | 1152/AD | 18/03/2025 | 17/05/2025 | VISHAL CONSTRUCTION CO. | 110.85 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Improvement of outdoor illumination arrangement with allied works at Zone-I PH No-1 of Madhabnagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. (SM/15525) | Assistant Engineer -II | Junior Engineer | ORD/000719/2025-2026 | 226/AE-II/SMD | 02/05/2025 | 23/05/2025 | WESTERN ENGINEERING CO. | 0.91 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15525 | New | Improvement of outdoor illumination arrangement with allied works at Zone-I PH No-2 of Madhabnagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte.(SM/15525) | Assistant Engineer -II | Junior Engineer | ORD/000725/2025-2026 | 227/AE-II/SMD | 02/05/2025 | 23/05/2025 | WESTERN ENGINEERING CO. | 0.91 | 0 | 0 | 100
Total | [13 empty] | 1176.78 | 79.53 | 6.76