## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/15526 | Augmentation | inking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kumirmari (Zone - II) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001321/2022-2023 | 11951/AD | 24/02/2023 | 26/03/2023 | M/S SEKH ENTERPRISE | 21.99 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/15526 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kumirmari W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001768/2022-2023 | 12041/AD | 27/02/2023 | 13/04/2023 | M/S. MIHIR KUMAR NASKAR | 8.56 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/15526 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Kumirmari (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001844/2022-2023 | 11541/AD | 16/02/2023 | 02/04/2023 | TECH VISION | 7.44 | 7.44 | 100 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/15526 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-II for Augmentation of Kumirmari water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000555/2022-2023 | 544/SMD | 21/02/2023 | 22/05/2023 | CHANDIMATA ELECTRICALS | 11.17 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/15526 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Kumirmari (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001082/2023-2024 | 3541/AD | 17/10/2023 | 16/11/2023 | SWASTIK CONSTRUCTION | 44.74 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/15526 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 263/AD | 24/04/2023 | 24/04/2023 | Resource Division | 105.54 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/15526 | Augmentation | Construction of OHR (350 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the KUMIRMARI (ZONE-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000252/2023-2024 | 1434/AD | 13/07/2023 | 01/03/2025 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 697.57 | 279.79 | 40.11 | 65
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/15526 | Augmentation | Construction of boundary wall at Head Work Site for Ground Water Based at Kumirmari Zone-II Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001228/2024-2025 | 5209/AD | 16/12/2024 | 30/01/2025 | SUDIP PRADHAN | 32.94 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/15526 | Augmentation | Renovation and retrofitting of Pump House No. 2 of Augmentation of Kumirmari W/S Scheme (Zone-II), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001405/2023-2024 | 1144/CSD | 01/11/2023 | 01/12/2023 | HALDER & CO. | 2.01 | 1.99 | 98.69 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/15526 | Augmentation | Renovation and retrofitting of Pump House No. 1 of Augmentation of Kumirmari W/S Scheme (Zone-II), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001404/2023-2024 | 1140/CSD | 31/10/2023 | 30/11/2023 | NASKAR ENTERPRISE | 2.15 | 2.07 | 95.92 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/15526 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000418/2023-2024 | 373/AD | 19/01/2024 | 19/01/2024 | Resource Division | 14.93 | 0 | 0 | 0
Total | [13 empty] | 949.04 | 291.29 | 30.69