## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001741/2022-2023 | 11768/AD | 21/02/2023 | 07/04/2023 | SOHAM ENTERPRISE | 8.92 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001740/2022-2023 | 11767/AD | 21/02/2023 | 07/04/2023 | SOHAM ENTERPRISE | 8.61 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001742/2022-2023 | 11772/AD | 21/02/2023 | 07/04/2023 | SOHAM ENTERPRISE | 8.61 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Conducting route survey, design distribution network and preparation & submission of DPR for Chimta (Zone - I & II)New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001887/2022-2023 | 11549/AD | 17/02/2023 | 03/04/2023 | M/S R.DUTTA & CO. | 7.4 | 7.4 | 100 | 0
5 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Inter c connection and rising main with supply of specials of Augmentation of Chimta (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000733/2023-2024 | 2894/AD | 19/09/2023 | 04/10/2023 | GANGA TUBEWELL AND HARDWARE | 9.27 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 380/AD | 02/05/2023 | 02/05/2023 | Resource Division | 45.96 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Chimta W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001117/2022-2023 | 11941/AD | 24/02/2023 | 10/04/2023 | AQUATECH ENGINEER | 44.84 | 18.31 | 40.83 | 30
8 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Laying of pipeline to connect the uncovered habitation at Chimta (Zone-I and II) W/S Scheme, Block - Gosaba, under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000280/2024-2025 | 2495/AD | 15/06/2024 | 28/09/2024 | SWASTIK CONSTRUCTION | 33.27 | 3.67 | 11.04 | 70
9 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Construction of boundary wall at Pump House No-2 for Ground water Based at Chimta (Zone-I & II)Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000741/2024-2025 | 4398/AD | 05/11/2024 | 05/12/2024 | MAA SANTOSHI ENTERPRISE | 15.13 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Chimta W/S Scheme (Zone-I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001116/2022-2023 | 11940/AD | 24/02/2023 | 10/04/2023 | AQUATECH ENGINEERS | 44.82 | 35.36 | 78.89 | 98
11 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Quotation for new service (Power) connection at Chimta Zone-I PH-1 Water supply scheme under Gosaba block Under SMD PHE dte. (Ref ID:-106609493) (App ID:-1007801321) |  |  | BILL/00381/2024-2025 | BP-2024-25-95 | 10/06/2024 | 10/06/2024 | WBSEDCL | 7.29 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Quotation for new service( power) connection at Chimta Zone-II PH-1 Water supply scheme under Gosba block Reference ID:-106652148, Application No :-1007883514 |  |  | BILL/02063/2024-2025 | BP-2024-25-492 | 09/12/2024 | 09/12/2024 | WBSEDCL | 5.28 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Quotation for new electrical connection at Chimta Zone-I, TW-02 Under Gosaba block. |  |  | BILL/00377/2024-2025 | BP-2024-25-94 | 10/06/2024 | 10/06/2024 | WBSEDCL | 4.51 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing ) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Chimta (Zone-I) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1117] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000032/2023-2024 | 125/AD | 13/04/2023 | 03/12/2024 | KHAN ENTERPRISE | 314.86 | 187.89 | 59.68 | 65
15 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I and P.H. No.1&2, ZoneII of Chimta water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000553/2022-2023 | 498/SMD | 20/02/2023 | 08/10/2025 | AVINABA ENGINEERING CONCERN | 40.18 | 0 | 0 | 45
16 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Chimta (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1117] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000296/2023-2024 | 1506/AD | 15/07/2023 | 10/05/2024 | MAA SANTOSHI ENTERPRISE | 314.54 | 98.85 | 31.43 | 39
17 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001739/2022-2023 | 11752/AD | 21/02/2023 | 01/11/2024 | SOHAM ENTERPRISE | 8.92 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Inter connection and rising main with supply of specials of Augmentation of Chimta (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001353/2023-2024 | 4425/AD | 06/12/2023 | 01/09/2024 | CHANDRA ENTERPRISE | 7.12 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Additional work of inter connection & rising main with supply of specials of Augmentation of Chimta (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000480/2024-2025 | 943/CSD | 22/08/2024 | 21/09/2024 | CHANDRA ENTERPRISE | 3.28 | 0 | 0 | 90
20 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | SM/15527 | New | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
Total | [13 empty] | 937.51 | 351.49 | 37.49