## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-VIII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/15530 | Augmentation | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VIII of Diamond Harbour-II Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001026/2022-2023 | 308/DHSD | 23/09/2022 | 23/10/2022 | GEO SOLUTION | 3.17 | 3.14 | 99.14 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-VIII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/15530 | Augmentation | Augmentation of laying distribution system including providing of Functional Household Tap Connection (FHTC) with allied works in Zone-VIII of Diamond Harbour-II block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 5302] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000372/2023-2024 | 1767/AD | 27/07/2023 | 16/07/2025 | SPA ENTERPRISE | 1008.05 | 239.12 | 23.72 | 55
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-VIII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/15530 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000140/2022-2023 | 17/AD | 05/04/2023 | 05/04/2023 | Resource Division | 34.48 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-VIII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/15530 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000429/2023-2024 | 3615/AD | 30/10/2023 | 30/10/2023 | Resource Division | 0.92 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-VIII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/15530 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000224/2023-2024 | 2207/AD | 10/08/2023 | 10/08/2023 | Resource Division | 27.63 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-VIII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/15530 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000615/2023-2024 | 276/AD | 15/01/2024 | 15/01/2024 | Resource Division | 31.72 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-VIII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/15530 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000738/2023-2024 | 568/AD | 27/01/2024 | 27/01/2024 | Resource Division | 9.72 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-VIII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/15530 | Augmentation | Interconnection from secondary grid to OHR and laying in the left-out portion of distribution system of different dia. DI pipes i.e. 200mm, 300mm, 450mm along with 63mm to 280mm UPVC pipes with allied road restoration work under augmentation scheme of Zone-IV of Diamond Harbour-II Block under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [SM/09508, SM/13912, SM/13914] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002529/2024-2025 | 814/AD | 27/02/2025 | 22/02/2026 | K.P. CONSTRUCTION | 146.09 | 0 | 0 | 52
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-VIII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/15530 | Augmentation | Additional balance Laying Distribution works under the Augmentation scheme of Zone-I at Diamond Harbour- II block for providing balance pipe lying works, including pipe carrying structure, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002491/2024-2025 | 782/AD | 25/02/2025 | 26/04/2025 | K.P. CONSTRUCTION | 83.24 | 0 | 0 | 0
Total | [13 empty] | 1345.04 | 242.27 | 18.01