## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000139/2022-2023 | 18/AD | 05/04/2023 | 05/04/2023 | Resource Division | 757.19 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000219/2023-2024 | 2202/AD | 10/08/2023 | 10/08/2023 | Resource Division | 37.76 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Augmentation of laying distribution system at Zone-II & Zone-III of Diamond Harbour-II Block for providing 100% FHTC at leftout areas within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - IIIB / C) [No. of FHTC = 2650] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000043/2023-2024 | 178/AD | 19/04/2023 | 13/03/2025 | SUNNY ELECTRIC CO. | 146 | 30.13 | 20.64 | 20
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-I of Diamond Harbour-II Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001517/2023-2024 | 432/DHSD | 22/09/2023 | 06/10/2023 | GEO SOLUTION | 0.84 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Construction of boundary wall (length - 145 m.) at proposed OHR site at Mouza - Akrapunji under Zone-II of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000869/2024-2025 | 4653/AD | 20/11/2024 | 19/01/2025 | MOUSUMI ENTERPRISE | 26.73 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-II of Diamond Harbour-II Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001521/2023-2024 | 433/DHSD | 22/09/2023 | 06/10/2023 | GEO SOLUTION | 0.84 | 0.84 | 100 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000737/2023-2024 | 567/ad | 27/01/2024 | 27/01/2024 | Resource Division | 245.4 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000919/2023-2024 | 1261/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.62 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000880/2023-2024 | 754/AD | 03/02/2024 | 03/02/2024 | Resource Division | 51.2 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Laying of distribution system at Zone-II of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001459/2021-2022 | 6072/AD | 17/02/2022 | 26/05/2025 | SAMIRON GHOSH | 479.57 | 94.32 | 19.67 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Restoration on bituminous road (PWD), protection work due to pipe laying (225 mm. to 350 mm. dia.) and supply of D.I specials within Zone-II under Diamond Harbour-II Block for MEGA SURFACE WATER BASED WATER SUPPLY SCHEME OF FALTA-MATHURAPUR, DISTRICT SOUTH 24 PARGANAS under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000445/2022-2023 | 5527/AD | 29/09/2022 | 05/07/2024 | GHOSH ENTERPRISE (II) | 22.78 | 11.78 | 51.7 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Augmentation of laying distribution system including construction of 1250 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system with allied works in Zone-II of Diamond Harbour-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8312] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000086/2023-2024 | 197/AD | 19/04/2023 | 01/02/2026 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 1011.34 | 37.14 | 3.67 | 25
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Laying of different dia pipes(DI pipe- 350mm to 400mm, UPVC- 90mm to 225mm) for the balance portion in the distribution system under Diamond Harbour II Block along with the Restoration of subsequent Bitumenous road and concrete road under the jurisdiction of PWD and Diamond Harbour II Panchayat Samiti / Block with the supply of DI specials and allied works of totaling 9453 mtr. under the Augmentation scheme of Diamond Harbour Zone-II within ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte.(Under Jal Jeevan Mission) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/002315/2023-2024 | 1092/AD | 22/02/2024 | 11/02/2026 | SAMIRON GHOSH | 264.14 | 0 | 0 | 85
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Balance works under the Augmentation scheme of Zone-II at Diamond Harbour- II block for providing House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002151/2024-2025 | 410/AD | 31/01/2025 | 02/03/2025 | M/S. S.S. ENTERPRISE | 16.15 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Balance works under the Augmentation scheme of Zone-I at Diamond Harbour- II block for providing House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002492/2024-2025 | 783/AD | 25/02/2025 | 11/04/2025 | K.P. CONSTRUCTION | 23.55 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Restoration by concreting of village road due to laying of pipeline dia. varies from 90 mm. to 350 mm. within Zone-II under Diamond Harbour-II Block for MEGA SURFACE WATER BASED WATER SUPPLY SCHEME OF FALTA-MATHURAPUR, SOUTH 24 PARGANAS under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000447/2022-2023 | 5528/AD | 29/09/2022 | 16/01/2025 | GHOSH ENTERPRISE (II) | 94 | 58.67 | 62.41 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Restoration of road and drain of damaged portion due to laying distribution and rising main pipeline from Raichoak more to Singhalganj F.P School under Zone- I of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD,Junior Engineer 3 DHSD | ORD/000528/2024-2025 | 3645/AD | 09/09/2024 | 08/11/2024 | K.P. CONSTRUCTION | 66.42 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | SM/15531 | Augmentation | Restoration of road damaged portion due to laying distribution and rising main pipeline from Singhalganj F.P School to Zone-I Head work site under Zone- I of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD,Junior Engineer 3 DHSD | ORD/001038/2024-2025 | 4957/AD | 04/12/2024 | 02/02/2025 | K.P. CONSTRUCTION | 47.76 | 0 | 0 | 100
Total | [13 empty] | 3292.28 | 232.89 | 7.07