## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIST | SM/15532 | Augmentation | Preparation of re-design, drawing for fundation considering pile cap for group piles for the proposed R.C.C. Over Head Reservoir at (Zone-I, OHR Size-1000 Cum., Mouza - Paschim Gobindapur) and (Zone-VII, OHR Size-600 Cum., Mouza - Kamarpole) of Diamond Harbour-II Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000366/2022-2023 | 199/DHSD | 27/07/2022 | 03/08/2022 | ASTER CONSULTANCY | 1 | 1 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIST | SM/15532 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2022-2023 | 19/AD | 05/04/2023 | 05/04/2023 | Resource Division | 96.26 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIST | SM/15532 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000218/2023-2024 | 2102/AD | 10/08/2023 | 10/08/2023 | Resource Division | 37.76 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIST | SM/15532 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000357/2023-2024 | 3221/AD | 04/10/2023 | 04/10/2023 | Resource Division | 0.21 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIST | SM/15532 | Augmentation | Construction of Platform of size 600mm x 600mm (inner dimension) for the FHTC along with road restoration at Zone-I & Zone-III of Diamond Harbour-II Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part-III A / B) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000042/2023-2024 | 177/AD | 19/04/2023 | 18/07/2023 | PRONICON INDIA | 164.18 | 134.33 | 81.82 | 50
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIST | SM/15532 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000613/2023-2024 | 275/AD | 15/01/2024 | 15/01/2024 | Resource Division | 49.28 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIST | SM/15532 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000879/2023-2024 | 753/AD | 03/02/2024 | 03/02/2024 | Resource Division | 0.33 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIST | SM/15532 | Augmentation | Restoration by concreting of village road due to laying of pipeline within Zone-I under Diamond Harbour-II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001180/2022-2023 | 11617/AD | 17/02/2023 | 09/09/2024 | K.P. CONSTRUCTION | 87.56 | 86.06 | 98.29 | 90
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIST | SM/15532 | Augmentation | Augmentation of laying distribution system including construction of 1000 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system with allied works in Zone-I at Paschim Gobindapur of Diamond Harbour- II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8053]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000017/2023-2024 | 58/AD | 10/04/2023 | 26/09/2025 | K.P. CONSTRUCTION | 866.96 | 724.15 | 83.53 | 84
Total | [13 empty] | 1303.53 | 945.55 | 72.54