## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15561 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001954/2022-2023 | 12690/AD | 14/03/2023 | 28/04/2023 | PODDER ENTERPRISE | 8.92 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15561 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001955/2022-2023 | 12691/AD | 14/03/2023 | 28/04/2023 | RIYAZ ENTERPRISE | 8.6 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15561 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Pathankhali (Zone - III) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000142/2023-2024 | 278/AD | 24/04/2023 | 08/06/2023 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 43.98 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15561 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone-III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000138/2023-2024 | 838/AD | 26/05/2023 | 10/06/2023 | M/S P. B. CONSTRUCTION | 7.5 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15561 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, Zone-III for Augmentation of Pathankhali supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000279/2023-2024 | 1139/SMD | 24/04/2023 | 23/07/2023 | M/S. S.R. ENTERPRISE | 29.83 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15561 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Pathankhali (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001889/2022-2023 | 11550/AD | 17/02/2023 | 03/04/2023 | M/S R.DUTTA & CO. | 4.29 | 4.29 | 100 | 99
7 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15561 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000412/2023-2024 | 368/AD | 19/01/2024 | 19/01/2024 | Resource Division | 6.36 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15561 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000719/2023-2024 | 540/AD | 25/01/2024 | 25/01/2024 | Resource Division | 22.19 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15561 | Augmentation | Construction of 250 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Pathankhali (Zone- III) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1032] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000037/2023-2024 | 172/AD | 19/04/2023 | 01/05/2025 | SAMSUL ENTERPRISE | 453.31 | 227.16 | 50.11 | 56
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15561 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 for Augmentation of Pathankhali Zone-III water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] (SM/15561) | Assistant Engineer | Junior Engineer | ORD/000078/2025-2026 | 1441/SMD | 22/05/2025 | 04/10/2025 | CMS ENGINEERING CONCERN | 10.87 | 0 | 0 | 0
Total | [13 empty] | 595.84 | 231.44 | 38.84