## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001957/2022-2023 | 12693/AD | 14/03/2023 | 28/04/2023 | BAPAN HALDAR | 8.57 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001984/2022-2023 | 12645/AD | 13/03/2023 | 27/04/2023 | RAJ & ENTERPRISE | 8.92 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Sadhupur (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000098/2023-2024 | 454/AD | 08/05/2023 | 23/05/2023 | MONDAL ENTERPRISE - 2 (SDK) | 16.47 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-II for Augmentation of Sadhupur Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000274/2023-2024 | 1133/SMD | 24/04/2023 | 23/07/2023 | DEBJYOTI BASU | 19.55 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | Construction of 300 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Sadhupur (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1161] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000023/2023-2024 | 150/AD | 18/04/2023 | 12/02/2024 | TANMAY ROY CHOWDHURY | 412.42 | 117.41 | 28.47 | 30
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | River crossing on the river bed and laying DI pipeline of Augmentation of Sadhupur W/S Scheme (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001033/2024-2025 | 4943/AD | 03/12/2024 | 01/02/2025 | SUBHO CONSTRUCTION | 78.35 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000723/2023-2024 | 545/AD | 25/01/2024 | 25/01/2024 | Resource Division | 111.13 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/05698/2023-2024 | BP-2023-24-607 | 28/03/2024 | 28/03/2024 | WBSEDCL | 5.17 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04815/2023-2024 | BP-2023-24-529 | 22/02/2024 | 22/02/2024 | WBSEDCL | 4.92 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Sadhupur (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001890/2022-2023 | 11551/AD | 17/02/2023 | 03/04/2023 | M/S R.DUTTA & CO. | 6.86 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | Construction of boundary wall at Pump House No - I for Gorund Water Based Piped Water Supply Scheme for Augmentation of Sadhupur (Zone - II) , Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000386/2025-2026 | 3371/AD | 16/07/2025 | 15/08/2025 | GANGA TUBEWELL AND HARDWARE | 11.16 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15563 | Augmentation | Construction of boundary wall at Pump House No. - 2 for Ground Water Based Piped Water Supply Scheme for Augmentation of Sadhupur (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000387/2025-2026 | 3372/AD | 16/07/2025 | 15/08/2025 | SOURAV DEBNATH | 10.36 | 0 | 0 | 0
Total | [13 empty] | 693.88 | 117.41 | 16.92