## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001894/2022-2023 | 11553/AD | 17/02/2023 | 03/04/2023 | INDRANIL DUTTA & ASSOCIATES | 3 | 3 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-III) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001790/2022-2023 | 12129/AD | 01/03/2023 | 15/04/2023 | BHATTACHARJEE & CO. | 39.86 | 35.92 | 90.11 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 229/AD | 24/04/2023 | 24/04/2023 | Resource Division | 14.27 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 1045/AD | 15/06/2023 | 15/06/2023 | Resource Division | 5.03 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Laying distribution system for Augmentation of Basanti (Zone - III) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000258/2023-2024 | 1446/AD | 13/07/2023 | 11/09/2023 | M/S SWAPAN KUMAR PRADHAN | 106.47 | 92.36 | 86.75 | 90
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti (Zone-III and VII) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1767] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000257/2023-2024 | 1445/AD | 13/07/2023 | 11/09/2023 | M/S SWAPAN KUMAR PRADHAN | 103.39 | 15.65 | 15.14 | 35
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-III of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/001502/2022-2023 | 873/SMD | 23/03/2023 | 21/06/2023 | JAI BHARAT COMMERCIAL CORPORATION | 20.82 | 20.37 | 97.84 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-III), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000494/2023-2024 | 1795/AD | 26/07/2023 | 09/09/2023 | B.S.ENTERPRISE | 7.35 | 6.91 | 93.96 | 98
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000495/2023-2024 | 1796/AD | 26/07/2023 | 09/09/2023 | B.S.ENTERPRISE | 7.09 | 6.61 | 93.15 | 98
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Basanti (Zone-III) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15564) | Assistant Engineer | Junior Engineer | ORD/002698/2023-2024 | 374/SMSD | 21/03/2024 | 05/04/2024 | JAI BHARAT COMMERCIAL CORPORATION | 0.58 | 0.58 | 100 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Basanti (Zone-III) W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti)(SM/15564) | Assistant Engineer | Junior Engineer | ORD/002699/2023-2024 | 375/SMSD | 21/03/2024 | 05/04/2024 | JAI BHARAT COMMERCIAL CORPORATION | 0.73 | 0.72 | 98.68 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 2 of Basanti (Zone-III) W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti)(SM/15564) | Assistant Engineer | Junior Engineer | ORD/002700/2023-2024 | 376/SMSD | 21/03/2024 | 05/04/2024 | JAI BHARAT COMMERCIAL CORPORATION | 0.9 | 0.9 | 99.81 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/04676/2023-2024 | BP-2023-24-507 | 12/02/2024 | 12/02/2024 | WBSEDCL | 17.69 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Restoration of Basanti Herobhanga Road from 0.00 kmp to 19.95km. block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division |  |  | BILL/01321/2024-2025 | BP-2024-25-683 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 107.4 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04002/2023-2024 | BP-2023-24-406 | 13/12/2023 | 13/12/2023 | WBSEDCL | 6.17 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-III) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000110/2023-2024 | 508/AD | 11/05/2023 | 02/03/2025 | SUPER CONSTRUCTION | 5.77 | 0 | 0 | 96
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 of Basanti (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti) | Assistant Engineer | Junior Engineer | ORD/001179/2024-2025 | 29/SMSD | 07/01/2025 | 22/01/2025 | SRI KRISHNA NIRMAN | 0.29 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Supply & installation of LED board at P.H. No- 1 & 2 of Basanti (Zone-III) water supply scheme, under South 24Pgs Mechanical Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000071/2024-2025 | 852/SMSD | 14/06/2024 | 29/06/2024 | FORTUNE ENGINEERING | 0.78 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15564 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Basanti (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti) | Assistant Engineer | Junior Engineer | ORD/001178/2024-2025 | 30/SMSD | 07/01/2025 | 22/01/2025 | SRI KRISHNA NIRMAN | 0.93 | 0 | 0 | 100
Total | [13 empty] | 448.55 | 183.03 | 40.8