## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/15566 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Sonakhali (Zone - IV) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001795/2022-2023 | 12130/AD | 01/03/2023 | 31/03/2023 | SAMIR GIRI | 19.56 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/15566 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Sonakhali (Zone-IV) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001842/2022-2023 | 11540/AD | 16/02/2023 | 02/04/2023 | TECH VISION | 3.08 | 3.08 | 100 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/15566 | Augmentation | onstruction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-IV) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001986/2022-2023 | 12647/AD | 13/03/2023 | 27/04/2023 | RINAS INFRASTRUCTURE | 7.08 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/15566 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Sonakhali (Zone-IV) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000150/2023-2024 | 695/AD | 18/05/2023 | 02/06/2023 | KHOKAN MONDAL | 15.59 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/15566 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-IV for Augmentation of Sonakhali Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/000290/2023-2024 | 2127/SMD | 30/05/2023 | 28/08/2023 | INDIA ENTERPRISE | 9.39 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/15566 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 242/AD | 24/04/2023 | 24/04/2023 | Resource Division | 38.11 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/15566 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-IV), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000315/2024-2025 | 2696/AD | 24/06/2024 | 08/08/2024 | GANGA TUBEWELL AND HARDWARE | 7.05 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/15566 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Sonakhali W/S Scheme (Zone-IV), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - III) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000745/2024-2025 | 4412/AD | 05/11/2024 | 05/12/2024 | TRIMURTI ENTERPRISE | 19.95 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/15566 | Augmentation | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD |  |  | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/15566 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/15566 | Augmentation | Repairing & renovation of Pump House no. - 2 of Sonakhali (Zone-IV) W/S Scheme Block - Basanti under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000284/2025-2026 | 689/CSD | 26/05/2025 | 25/06/2025 | KIRON CONSTRUCTION | 3.42 | 0 | 0 | 0
Total | [13 empty] | 3163.79 | 3.08 | 0.1