## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Canning-II | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHAGRA UNDER ALIPORE DIVISION, BLOCK-CANNING-II, DISTRICT-SOUTH 24 PARGANAS | SM/15577 | New | Conducting route survey, design distribution network and preparation & submission of DPR for Khagra New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001893/2022-2023 | 11552/AD | 17/02/2023 | 03/04/2023 | INDRANIL DUTTA & ASSOCIATES | 1.59 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Canning-II | S24 Pgns Mechanical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHAGRA UNDER ALIPORE DIVISION, BLOCK-CANNING-II, DISTRICT-SOUTH 24 PARGANAS | SM/15577 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Khagra supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000270/2023-2024 | 1130/SMD | 24/04/2023 | 23/07/2023 | MOUMITA ENTERPRISE | 9.43 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Canning-II | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHAGRA UNDER ALIPORE DIVISION, BLOCK-CANNING-II, DISTRICT-SOUTH 24 PARGANAS | SM/15577 | New | Material Requisition To Resource Division |  |  | RTOR000734/2023-2024 | 558/AD | 25/01/2024 | 25/01/2024 | Resource Division | 1.18 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Canning-II | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHAGRA UNDER ALIPORE DIVISION, BLOCK-CANNING-II, DISTRICT-SOUTH 24 PARGANAS | SM/15577 | New | Sinking of 150 X 100 mm dia. 360Mtr. Depth Rig bored Tube wells for the Khagra Mini Piped Water Supply Scheme, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001807/2022-2023 | 12131/AD | 01/03/2023 | 23/05/2025 | B.K. ENTERPRISE. | 15.65 | 0 | 0 | 95
5 | SOUTH 24 PARGANAS | Canning-II | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHAGRA UNDER ALIPORE DIVISION, BLOCK-CANNING-II, DISTRICT-SOUTH 24 PARGANAS | SM/15577 | New | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Khagra, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 542] (TSM/017752) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000119/2023-2024 | 555/AD | 12/05/2023 | 10/08/2023 | MAJUMDER ENTERPRISE | 208.66 | 0 | 0 | 86
Total | [13 empty] | 236.51 | 0 | 0