## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Dhuri Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001917/2022-2023 | 11776/AD | 21/02/2023 | 07/04/2023 | INDRANIL DUTTA & ASSOCIATES | 6.37 | 6.37 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dhuri W/S Scheme , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001818/2022-2023 | 12158/AD | 01/03/2023 | 15/04/2023 | HI TECH ENTERPRISE | 7.35 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03416/2023-2024 | BP-2023-24-371 | 13/11/2023 | 13/11/2023 | WBSEDCL | 4.16 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, for Augmentation of Dhuri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/000495/2022-2023 | 297/SMD | 03/02/2023 | 04/05/2023 | WEST BENGAL ENGINEERING CO. | 22.21 | 10.04 | 45.22 | 40
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the DHURI, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000061/2023-2024 | 311/AD | 26/04/2023 | 14/07/2025 | SAMSUL ENTERPRISE | 451.63 | 300.27 | 66.49 | 80
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Augmentation Piped Water Supply Scheme of Dhuri W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000774/2024-2025 | 4476/AD | 11/11/2024 | 26/12/2024 | M/S P. B. CONSTRUCTION | 50.82 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Augmentation Piped Water Supply Scheme of Dhuri W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000775/2024-2025 | 4477/AD | 11/11/2024 | 11/12/2024 | M/S ASHA ENGINEERING | 13.14 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 4 of Dhuri W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti)(SM/15834) | Assistant Engineer | Junior Engineer | ORD/002682/2023-2024 | 337/SMSD | 14/03/2024 | 29/03/2024 | WEST BENGAL ENGINEERING CO. | 0.89 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-3 & 4 of of Dhuri W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15834) | Assistant Engineer | Junior Engineer | ORD/002680/2023-2024 | 335/SMSD | 14/03/2024 | 29/03/2024 | WEST BENGAL ENGINEERING CO. | 0.58 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dhuri W/S Scheme , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001819/2022-2023 | 12159/AD | 01/03/2023 | 15/04/2023 | HI TECH ENTERPRISE | 7.09 | 6.85 | 96.55 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 539/AD | 25/01/2024 | 25/01/2024 | Resource Division | 49.66 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/15834 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 3 of Dhuri W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti)(SM/15834) | Assistant Engineer | Junior Engineer | ORD/002681/2023-2024 | 336/SMSD | 14/03/2024 | 29/03/2024 | WEST BENGAL ENGINEERING CO. | 0.9 | 0 | 0 | 100
Total | [13 empty] | 3239.3 | 323.54 | 9.99