## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-III), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS. | SM/15954 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Gosaba (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001926/2022-2023 | 11799/AD | 22/02/2023 | 08/04/2023 | M/S R.DUTTA & CO. | 3.18 | 3.18 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-III), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS. | SM/15954 | Augmentation | Construction of OHR (150 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the Gosaba (Zone-III), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [TSM/018434] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000034/2023-2024 | 275/AD | 24/04/2023 | 18/02/2024 | I.S. ENTERPRISE | 325.97 | 37.63 | 11.55 | 35
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-III), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS. | SM/15954 | Augmentation | Sinking of 01 (one) no. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-III), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. - 1) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001194/2023-2024 | 3999/AD | 21/11/2023 | 21/12/2023 | MEHAI TECHNOLOGY LIMITED | 22.45 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-III), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS. | SM/15954 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000408/2023-2024 | 362/AD | 19/01/2024 | 19/01/2024 | Resource Division | 7.37 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-III), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS. | SM/15954 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000722/2023-2024 | 544/AD | 25/01/2024 | 25/01/2024 | Resource Division | 40.24 | 0 | 0 | 0
Total | [13 empty] | 399.21 | 40.81 | 10.22