## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-VIII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001938/2022-2023 | 11809/AD | 22/02/2023 | 08/04/2023 | INDRANIL DUTTA & ASSOCIATES | 0.67 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Construction of 400 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of Basanti (Zone-VIII) piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000033/2023-2024 | 127/AD | 13/04/2023 | 07/02/2024 | M/S. SIKHA ENTERPRISE | 134.28 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Laying distribution system for Augmentation of Basanti W/S Scheme (Zone-VIII), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000054/2023-2024 | 146/AD | 17/04/2023 | 16/06/2023 | M/S ROY TRADING CO. | 207.68 | 0 | 0 | 85
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Laying of pipeline at different points of Basanti W/S Scheme (Zone-VIII),Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000091/2023-2024 | 447/AD | 08/05/2023 | 23/05/2023 | MAA BHABANI CONSTRUCTION (DUM DUM) | 7.91 | 0 | 0 | 30
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 233/AD | 24/04/2023 | 24/04/2023 | Resource Division | 69.7 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 1043/AD | 15/06/2023 | 15/06/2023 | Resource Division | 12.09 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti W/S Scheme (Zone-VIII), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1963] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000055/2023-2024 | 147/AD | 17/04/2023 | 16/06/2023 | M/S ROY TRADING CO. | 111.41 | 0 | 0 | 55
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VIII), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001994/2022-2023 | 12685/AD | 14/03/2023 | 28/04/2023 | PATRA CONSTRUCTION | 7.21 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VIII) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001995/2022-2023 | 12686/AD | 14/03/2023 | 28/04/2023 | PIU ENTERPRISE | 6.96 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD |  |  | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04626/2023-2024 | BP-2023-24-483 | 07/02/2024 | 07/02/2024 | WBSEDCL | 5.09 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04707/2023-2024 | BP-2023-24-519 | 17/02/2024 | 17/02/2024 | WBSEDCL | 18.35 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Charges for new service connection at Basanti (Zone-VIII) Pump house no-3 |  |  | BILL/00524/2024-2025 | BP-2024-25-124 | 24/06/2024 | 24/06/2024 | WBSEDCL | 7.57 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 Zone-VIII of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/001510/2022-2023 | 887/SMD | 24/03/2023 | 01/07/2026 | M/S. S.R. ENTERPRISE | 31.73 | 0 | 0 | 65
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1, 2 & 3 of Basanti (Zone-VIII) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15957) | Assistant Engineer | Junior Engineer | ORD/001402/2024-2025 | 31/SMSD | 07/01/2025 | 01/06/2025 | M/S. S.R. ENTERPRISE | 0.87 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of Basanti (Zone-VIII) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15957) | Assistant Engineer | Junior Engineer | ORD/001403/2024-2025 | 34/SMSD | 07/01/2025 | 01/06/2025 | M/S. S.R. ENTERPRISE | 0.91 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Basanti W/S Scheme (Zone-VIII), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001870/2022-2023 | 12462/AD | 10/03/2023 | 06/10/2024 | SOMA ENTERPRISE | 58.79 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VIII) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001996/2022-2023 | 12694/AD | 14/03/2023 | 01/01/2025 | S.MITRA & CO. | 6.96 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15957 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-VIII) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000094/2023-2024 | 450/AD | 08/05/2023 | 02/05/2025 | MAA BHABANI CONSTRUCTION (DUM DUM) | 10.08 | 0 | 0 | 100
Total | [13 empty] | 1114.35 | 0 | 0