## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Narayangar (Part-B) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001846/2022-2023 | 11813/AD | 23/02/2023 | 09/04/2023 | TECH VISION | 4.6 | 4.6 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Narayangar (Part-B) W/S Scheme, Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002019/2022-2023 | 12925/AD | 16/03/2023 | 30/04/2023 | SWASTIK CONSTRUCTION | 22.8 | 0 | 0 | 81
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Narayangar (Part-B), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1542] (TSM/018335) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000083/2023-2024 | 196/AD | 19/04/2023 | 18/07/2023 | EQUIPMENTS & SPARES AGENCIES | 255.63 | 155.95 | 61.01 | 85
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Narayangarh Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000598/2023-2024 | 2368/SMD | 30/06/2023 | 03/06/2025 | A.S.ENTERPRISE | 27 | 25.3 | 93.7 | 85
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000135/2023-2024 | 690/AD | 18/05/2023 | 17/07/2023 | SNEHA CONSTRUCTION | 58.66 | 53.11 | 90.53 | 95
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000466/2023-2024 | 1928/AD | 01/08/2023 | 15/09/2023 | A.R.CONSTRUCTION | 7.35 | 6.57 | 89.44 | 98
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000467/2023-2024 | 1929/AD | 01/08/2023 | 15/09/2023 | A.R.CONSTRUCTION | 7.09 | 6.28 | 88.53 | 98
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000468/2023-2024 | 1930/AD | 01/08/2023 | 15/09/2023 | A.R.CONSTRUCTION | 7.09 | 6.61 | 93.25 | 98
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 114/AD | 13/04/2023 | 13/04/2023 | Resource Division | 0.34 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 267/AD | 24/04/2023 | 24/04/2023 | Resource Division | 27.5 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 849/AD | 27/05/2023 | 27/05/2023 | Resource Division | 1.72 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02962/2023-2024 | BP-2023-24-292 | 11/10/2023 | 11/10/2023 | WBSEDCL | 9.54 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03521/2023-2024 | BP-2023-24-385 | 23/11/2023 | 23/11/2023 | WBSEDCL | 41.14 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Augmentation of Narayangarh piped water supply scheme of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (SM/15961) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000569/2024-2025 | 3979/AD | 27/09/2024 | 16/12/2026 | GHOSH ENTERPRISE (II) | 138.78 | 0 | 0 | 25
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Supply & installation of LED board at P.H. No-1 & 2 of Narayangarh (Aug) water supply scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000100/2024-2025 | 523/SMSD | 26/04/2024 | 11/05/2024 | COOLING CARE CENTER | 0.78 | 0.78 | 100 | 100
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House-3 Part-B of Narayangargh water supply sche under SMD,PHE Dte. (Block-Canning-I) (SM/15961) | Assistant Engineer | Junior Engineer | ORD/001959/2024-2025 | 1538/SMSD | 21/11/2024 | 06/12/2024 | A.S.ENTERPRISE | 0.8 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House-1 Part-B of Narayangargh water supply sche under SMD,PHE Dte. (Block-Canning-I) (SM/15961) | Assistant Engineer | Junior Engineer | ORD/001960/2024-2025 | 1181/SMSD | 20/08/2024 | 04/09/2024 | A.S.ENTERPRISE | 0.8 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Narayangarh Part-B, PH-2, under Canning-I Block water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002947/2023-2024 | 159/SMSD | 05/02/2024 | 20/02/2024 | A.S.ENTERPRISE | 0.88 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | SM/15961 | Augmentation | Supply delivery of standby submersible pump motor at Narayangargh Part-B PH-1 water supply scheme Under SMD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000385/2024-2025 | 1028/SMSD | 15/07/2024 | 30/07/2024 | NARAYAN ENTERPRISE | 0.52 | 0 | 0 | 100
Total | [13 empty] | 3237.51 | 259.21 | 8.01