## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-IX) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001939/2022-2023 | 11810/AD | 22/02/2023 | 08/04/2023 | INDRANIL DUTTA & ASSOCIATES | 5.49 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of Basanti (Zone-IX) piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000053/2023-2024 | 144/AD | 13/04/2023 | 07/02/2024 | RIVER BENZ CONSTRUCTION | 141.92 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IX), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000499/2023-2024 | 1799/AD | 26/07/2023 | 09/09/2023 | PAL ENTERPRISE | 7.35 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IX) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000500/2023-2024 | 1800/AD | 26/07/2023 | 09/09/2023 | STRINGS ENGINEERING PVT. LTD. | 7.1 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 234/AD | 24/04/2023 | 24/04/2023 | Resource Division | 74.55 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 1055/AD | 15/06/2023 | 15/06/2023 | Resource Division | 9.81 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti W/S Scheme (Zone-IX), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1593] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000056/2023-2024 | 148/AD | 17/04/2023 | 15/02/2025 | M.T.C. CONSTRUCTION | 91.45 | 0 | 0 | 30
8 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IX) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000501/2023-2024 | 1801/AD | 26/07/2023 | 09/09/2023 | SAMIR GIRI | 7.09 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Laying of additional pipe line for Augmentation of Basanti W/S Scheme (Zone-IX), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002181/2023-2024 | 832/AD | 05/02/2024 | 06/03/2024 | NAZRUL ENTERPRISE | 8.2 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/04677/2023-2024 | BP-2023-24-505 | 12/02/2024 | 12/02/2024 | WBSEDCL | 10.24 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Charges for new service connection at pump house no-3 of Basanti (Zone-IX) water supply scheme.(Basanti Block) |  |  | BILL/01812/2024-2025 | BP-2024-25-459 | 29/10/2024 | 29/10/2024 | WBSEDCL | 13.3 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Basanti W/S Scheme (Zone-IX), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001871/2022-2023 | 12463/AD | 10/03/2023 | 08/08/2024 | SOMA ENTERPRISE | 58.76 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Laying distribution system for Augmentation of Basanti W/S Scheme (Zone-IX), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [TSM/018392] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000167/2023-2024 | 978/AD | 08/06/2023 | 28/01/2025 | RIVER BENZ CONSTRUCTION | 146.19 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 Zone-IX of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/001515/2022-2023 | 895/SMD | 27/03/2023 | 01/07/2025 | SINHA ELECTRICALS | 31.38 | 0 | 0 | 60
15 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-IX) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000729/2023-2024 | 2890/AD | 19/09/2023 | 04/10/2023 | SURYA ENTERPRISE | 10.48 | 0 | 0 | 90
16 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Construction of boundary wall at Pump House No. 3 for Augmentation of Basanti (Zone-IX) Piped Water Supply Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001226/2024-2025 | 5225/AD | 16/12/2024 | 27/12/2025 | NEW DAWN POWER & CONSTRUCTION | 13.34 | 0 | 0 | 80
17 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Laying additional pipe line with other allied works at Basanti (Zone-IX) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000829/2024-2025 | 4535/AD | 13/11/2024 | 12/01/2025 | S.S. CONSTRUCTION | 38.57 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1,2 & 3 of Basanti (Zone-IX) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15963) | Assistant Engineer | Junior Engineer | ORD/001524/2024-2025 | 1714/SMSD | 27/12/2024 | 11/01/2025 | SINHA ELECTRICALS | 0.87 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Basanti (Zone-IX) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15963) | Assistant Engineer | Junior Engineer | ORD/001525/2024-2025 | 1715/SMSD | 27/12/2024 | 11/01/2025 | SINHA ELECTRICALS | 0.91 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Supply & installation of LED board at P.H. No-1 & 2 of Basanti (Zone-IX) water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Basanti] | Assistant Engineer | Junior Engineer | ORD/001518/2024-2025 | 257/SMSD | 20/02/2025 | 07/03/2025 | KARTICK BAL | 0.78 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Construction of Toilet including Sanitary arrangement at the site for Augmentation of Basanti (Zone - IX) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House - 3 (Old)] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000457/2025-2026 | 816/CSD | 17/06/2025 | 17/07/2025 | M/S NABIBAR BUILDERS | 1.91 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | SM/15963 | Augmentation | Construction of Toilet including Sanitary arrangement at the site for Augmentation of Basanti (Zone - IX) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House - 1 (Old)] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000727/2025-2026 | 815/CSD | 17/06/2025 | 17/07/2025 | ASIK CONSTRUCTION | 1.91 | 0 | 0 | 0
Total | [13 empty] | 681.59 | 0 | 0