## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Sadhupur (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000097/2023-2024 | 453/AD | 08/05/2023 | 23/05/2023 | UNIVERSAL CONSTRUCTION | 19.52 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3, Zone-I for Augmentation of Sadhupur Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000293/2023-2024 | 2129/SMD | 31/05/2023 | 02/01/2026 | SUBHRA ENTERPRISE | 29.32 | 0 | 0 | 90
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Sadhupur (Zone-I) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 2159] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001195/2023-2024 | 4045/AD | 22/11/2023 | 17/09/2024 | SUPRITI ENTERPRISE | 648.45 | 261.55 | 40.33 | 30
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001956/2022-2023 | 12692/AD | 14/03/2023 | 01/01/2025 | BAPAN HALDAR | 8.88 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Sadhupur (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001931/2022-2023 | 11804/AD | 22/02/2023 | 08/04/2023 | M/S R.DUTTA & CO. | 6.53 | 6.53 | 100 | 95
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Sadhupur W/S Scheme (Zone - I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002033/2022-2023 | 13029/AD | 24/03/2023 | 23/05/2023 | GIASHUDDIN CONSTRUCTION | 65.85 | 14.67 | 22.28 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002039/2022-2023 | 13035/AD | 24/03/2023 | 01/02/2025 | MAA SOLAR ENTERPRISE | 8.61 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002040/2022-2023 | 13036/AD | 24/03/2023 | 01/02/2025 | MAA SOLAR ENTERPRISE | 8.61 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 379/AD | 02/05/2023 | 02/05/2023 | Resource Division | 67.54 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Supply delivery of Valve & UPVC column pipe etc. at Zone-I PH-3 Aug of Sadhupur water supply scheme under Gosaba Block under SMD, P.H.E. Dte. (SM/15965) | Assistant Engineer | Junior Engineer | ORD/002441/2024-2025 | 1726/SMSD | 27/12/2024 | 11/01/2025 | SUBHRA ENTERPRISE | 0.7 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Supply delivery of Valve & UPVC column pipe etc. at Zone-I PH-1 Aug of Sadhupur water supply scheme under Gosaba Block under SMD, P.H.E. Dte. (SM/15965) | Assistant Engineer | Junior Engineer | ORD/002442/2024-2025 | 1676-A-SMSD | 20/12/2024 | 04/01/2025 | SUBHRA ENTERPRISE | 0.7 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Supply delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Aug of Sadhupur Zone-I, PH-3 water supply scheme under Gosaba block Under SMD PHE Dte. (SM/15965) | Assistant Engineer | Junior Engineer | ORD/002445/2024-2025 | 1768/SMSD | 31/12/2024 | 15/01/2025 | SUBHRA ENTERPRISE | 0.99 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Supply delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Aug of Sadhupur Zone-I, PH-1 water supply scheme under Gosaba block Under SMD PHE Dte. (SM/15965) | Assistant Engineer | Junior Engineer | ORD/002446/2024-2025 | 1766/SMSD | 31/12/2024 | 15/01/2025 | SUBHRA ENTERPRISE | 0.99 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Supply delivery of Valve & UPVC column pipe etc. at Zone-I PH-2 Aug of Sadhupur water supply scheme under Gosaba Block under SMD, P.H.E. Dte. (SM/15965) | Assistant Engineer | Junior Engineer | ORD/002443/2024-2025 | 1725/SMSD | 27/12/2024 | 11/01/2025 | SUBHRA ENTERPRISE | 0.7 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Supply delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Aug of Sadhupur Zone-I, PH-2 water supply scheme under Gosaba block Under SMD PHE Dte. (SM/15965) | Assistant Engineer | Junior Engineer | ORD/002444/2024-2025 | 1767/SMSD | 31/12/2024 | 15/01/2025 | SUBHRA ENTERPRISE | 0.99 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Construction of boundary wall at Pump House No. - 2 for Ground Water Based Piped Water Supply Scheme for Augmentation of Sadhupur (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000123/2025-2026 | 2586/AD | 03/06/2025 | 03/07/2025 | KHAN CONSTRUCTION (BASANTI) | 10.27 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Supply & fixing main switch & Bus Bar at Zone-I, Pump House-1,2, & 3 of Aug of Sadhupur water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/15965) | Assistant Engineer | Junior Engineer | ORD/001856/2024-2025 | 105/SMSD | 21/01/2025 | 05/02/2025 | SUBHRA ENTERPRISE | 0.92 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I, Pump House-1 of Aug of Sadhupur water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/15965) | Assistant Engineer | Junior Engineer | ORD/002422/2024-2025 | 125/SMSD | 22/01/2025 | 06/02/2025 | SUBHRA ENTERPRISE | 0.97 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I, Pump House-2 of Aug of Sadhupur water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/15965) | Assistant Engineer | Junior Engineer | ORD/002423/2024-2025 | 126/SMSD | 22/01/2025 | 06/02/2025 | SUBHRA ENTERPRISE | 0.97 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I, Pump House-3 of Aug of Sadhupur water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/15965) | Assistant Engineer | Junior Engineer | ORD/002419/2024-2025 | 136/SMSD | 22/01/2025 | 06/02/2025 | SUBHRA ENTERPRISE | 0.97 | 0 | 0 | 100
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15965 | Augmentation | Quotation for new service( power) connection at Sadhupur Zone-I PH-2 Water supply scheme under Gosaba block. Reference ID:-106878331, Application No :-1008293283 |  |  | BILL/02622/2024-2025 | BP-2024-25-563 | 28/01/2025 | 28/01/2025 | WBSEDCL | 8.25 | 0 | 0 | 0
Total | [13 empty] | 890.7 | 282.75 | 31.74